PROPOSED INTERNAL ALTERATIONS (PHASES 1 & 2)

- at –

XPLORE! SCIENCE DISCOVERY CENTRE, WREXHAM

- for –

NORTH WALES SCIENCE

FORM OF TENDER

The Form of Tender must be uploaded to the Sell2Wales procurement portal by 12.00 noon on Friday 31 October 2025.

To:	North Wales Science

To whom it may concern

I/We having read the conditions of contract and Bills of Quantities delivered to me/us and having examined the drawings and documents referred to therein, do hereby offer to execute and complete in accordance with the conditions of contract the whole of the works described for the Firm Price Sum of:

£                                               :                     p (excluding VAT)

(

)

based on the following (refer to Clause A13/130 in the Preliminaries for full description of Sections):

| Section | Description | Date of Possession | Completion | Duration |
| --- | --- | --- | --- | --- |
| Section1 | Alterations to first floor | Mon 5 January 2026 | Fri 27 March 2026 | 12 weeks |
| Section 2 | Alterations to ground floor | Mon 30 March 2026 | Fri 17 July 2026 | 16 weeks |

Date by which the Contractor requires an order to enable works to start on site on Monday 5 January 2026, is                                                       (INSERT DATE)

I/We confirm that I/we have visited the site.

I/We agree that should any obvious errors in pricing or arithmetic errors be discovered before acceptance of this offer in the priced Bills of Quantities submitted by me/us these errors will be dealt with in accordance with Alternative 1 contained in JCT Practice Note 6 (Series 2) “Main Contract Tendering”.

This Tender remains open for consideration for 12 weeks from the date fixed for the submission or lodgement of tenders.

Dated this			day of 		2025

Name

Address

Signature

NOTE:	The Employer does not bind itself to accept the lowest or any tender or be liable for any expense in the preparation thereof.