Request for Quote (RfQ) for Business Continuity Planning

Contract Title:  Business Continuity Planning

Contract Reference:  CCHA-(2025-2026)-019

Date: 29/10/2025

Submission due date: 26/11/2025

Contract Manager: Rhys Hutchings

Request for Quote from:

Cardiff Community Housing Association Limited

Tolven Court Dowlais Road

Cardiff

CF24 5LQ

Reg no: 21667R

Quote for (bidders to populate):

[NAME]

[Company name]

[Company address]

[Company phone & email address]

[Date submitted]

[reg. no xxx]

Dear Bidder,

I’m writing on behalf of Cardiff Community Housing Association Limited “CCHA” (the “Buyer”) to request a formal quote on providing BCP Policy Enhancement & Playbook Integration .

To procure services for the enhancement of the organization’s Business Continuity Planning (BCP), including the development of detailed playbook activity documents and the review and customization of the overarching BCP document.

- Term:

The contract will cover provision of consultancy service required commencing in December 2025 for the length of 12 weeks.

- Requirements

Scope of works

A. Playbook Activity Documentation

For each BCP playbook activity listed in the current register, the supplier must produce a 1–2-page document that includes:

- Severity Level: Clear classification of the activity’s impact (e.g., Category 1, 2, or 3).

- Involved Personnel: Identification of roles and teams required to respond (e.g., CLT, OMT, Managers, Staff).

- Response Summary: Concise description of the response actions, escalation procedures, and communication plans.

- Dependencies: Systems, services, or external partners involved in the response.

- Review Date: Suggested frequency for review and update of each playbook.

Playbook Activities (This is a guide and may not be the exhaustive list)

| Department | Activity |
| --- | --- |
| Assets | Death from a property defect |
| Assets & Housing | Inclement weather |
| People | Insider Threats & Malicious Actions |
| Housing | Open Housing disruption in service |
| Housing | Unexplained Death at a property |
| Housing | Health crisis |
| Housing | Serious ASB/ crime |
| Office | Lockdown/Threat type incident at office |
| Housing | Issue with Loudoun- emergency issue |
| Housing | Support provider- goes under/ gives notice |
| Assets | Legionella outbreak |
| Assets | Commercial lift out of service |
| Assets & Housing | Fire- Major |
| Assets & Housing | Explosion |
| Assets & Repairs | Supply chain disruption |
| Repairs | Connect system disruption in service |
| Repairs/ Housing | Community unrest e.g. riots |
| People | Resource Unavailability |
| People | Loss of Key People |
| IT | Microsoft programs disruption in service |
| IT | Malware Breach |
| IT | Cyber Incident |
| IT | Phone System Outage |
| IT | Office WIFI Outage |
| IT | Mobile Phone Outage |
| Finance | Finance payment system disruption in service |
| Finance | Finance hack/scam wiping current account |
| Finance | Payment of Salaries / Allowances |
| Governance | Data Breach- Major |
| Governance | Data Breach- Intermediate |
| All | War |
| Development | On site Fire - Major |
| Development | Death / serious injury on site |

B. Overarching BCP Document Review

- Review the existing overarching BCP document.

- Modify and tailor the document to reflect the specific operational and structural context of the organization.

- Integrate the newly developed playbook activity documents into the overarching BCP framework.

- Ensure alignment with regulatory requirements, sector best practices, and internal governance standards.

- Provide a version-controlled master document and a summary of changes made.

Deliverables

- Individual playbook activity documents (1–2 pages each) in an editable word format.

- Updated overarching BCP document with embedded or linked playbook activities.

- Summary report outlining methodology, changes, and recommendations for future updates.

Timeline

- Initial draft of BCP document: 4 weeks of contract award.

- Draft playbook documents: within 8 weeks of contract award.

- Final version of all documents: within 12 weeks.

Review meetings: bi-weekly progress updates.

Evaluation Criteria

- Demonstrated experience in BCP development and production of BCP Playbook documentation.

- Understanding housing, asset management, IT, and people-related risks.

- References from similar projects.

- Commercial Response (bidder to populate):

Please quote for each element of the service.  The price submitted should be the rate required to provide the specific service, as set out in the scope (section1), and excluding VAT.  Note that the budget range for this project is between £5,000 - £10,000 excluding VAT.

12 weeks:

| Item ID | Description | Quantity | Unit Price (excl. VAT) | Total cost (excl. VAT) |
| --- | --- | --- | --- | --- |
|  |  |  | Total cost (excl. VAT) |  |

- RfQ Timetable

The key dates for this Procurement are currently anticipated to be as follows:

| Stage: | Date: | Initiated by: | Submit to: |
| --- | --- | --- | --- |
| RfQ issued | 29-Oct-25 | The Buyer | All Bidders |
| Deadline for clarification questions | 19-Nov-25 at 5pm | Bidder | The Buyer |
| The Buyer publishes answers to the final clarification questions | 21-Nov-25 | The Buyer | All Bidders |
| Bid deadline | 26-Nov-25 at 2pm | Bidder | The Buyer |
| Bid evaluation | w/c 3-Dec-25 | The Buyer | N/A |
| Bid moderation | w/c 3-Dec-25 | The Buyer | N/A |
| Contract award | Week commencing 10-Dec-25 | The Buyer | The successful bidder(s), now ‘supplier’. |

Please send any clarification questions to Sell2Wales postbox by the 19th of November at 17:00.

Please provide your response via Sell2Wales by 21st November at 14:00.

- Award Criteria

CCHA assesses a proposal based on a combination of Quality/Technical, Social Value and Commercial elements. The Buyer shall award the Contract to the Tenderer which submits the highest scoring response.

Any responses that score 40 or below will automatically be excluded from proceeding to the commercial stage, and therefore the bidder will be eliminated from the procurement process.

The table below shows the evaluation ratio:

| 1. Quality |  |  |  |
| --- | --- | --- | --- |
| # | Criteria | Weighting | Comments |
| 1.1 | Based on the requirements stated above, pick one activity from the playbook list and produce one playbook. The example is to be maximum 2 A4 word document, Arial 12pt. | 30% | Word Limit: 1000 |
| 1.2; What is the project team/staff that would be allocated to this contract including their roles and responsibilities. Please also include their relevant expertise for this project.; 15%; Word Limit: 500. 1.3; What is your expertise working for social housing clients; 15%; Word Limit: 250.. |
| 2. Social Value |  |  |  |
| # | Criteria | Weighting | Comments |
| 2.1 | Please detail what added value your organisation will deliver in relation to CCHA’s Community Benefits commitment to our tenants, residents and communities. What will you offer and how will you monitor and measure this throughout the course of the contract? Please refer to our Community Benefits Statement. | 10% | Word Limit: 400 |
| 3. Price* |  |  |  |
| # | Criteria | Weighting | Comments |
| 3.1 | Please detail the cost for delivering a review of the existing BCP policy and creation of the playbooks and integration of the two documents. | 30% | Please populate section 3 |

- Quality/Technical and Social Value Scoring

Responses will be scored in the following manner:

| Capability | Evidence | Remark | Scores |
| --- | --- | --- | --- |
| Bidder is likely to be able to meet the needs of the project. | Evidence is consistent, comprehensive, compelling, directly relevant to the project in all respects and highly credible (by being substantiated by independent sources where possible.) | Absolute Confidence | 100 |
|  | Evidence is sufficient, convincing, and credible. | Confidence | 80 |
| Small risk that Bidder will not be able to meet the needs of the project. | Evidence has minor gaps, or to a small extent is unconvincing, lacks credibility or irrelevant to the project. | Minor Concerns | 60 |
| Moderate risk that the Bidder will not be able to meet the needs of the project. | Evidence has moderate gaps, is unconvincing. | Moderate Concerns | 40 |
| Significant risk that the Bidder will not be able to meet the needs of the project. | Evidence has major gaps, is unconvincing, lacks credibility, or irrelevant to the project. | Major Concerns | 20 |
| Bidder will not be able to meet the needs of the project. | No evidence or misleading evidence. | Not acceptable | 0 |

- Commercial Scoring

For the pricing element, the total marks available for price shall be 30%. The marks for commercial shall be calculated based on the lowest priced complaint day rate gaining the full % available with the remaining quotes being allocated marks using the following formula (rounded to 2 decimal points):

| Score = | Lowest Tender Price | 30 % available |
| --- | --- | --- |
|  | Tender Price |  |

- Terms and Conditions

CCHA will be using their own standard Contractual Terms and Conditions to form the agreement, should the proposed terms not be viable.

CCHA would like to thank your organisation for showing an interest in this requirement and we look forward to receiving your proposal via Sell2Wales by 26th November at 14:00.

Kind regards,

Monia Lisa Carvalho

Senior Procurement Officer