## Yew Close - Price Schedule
Merthyr Valleys Homes - Demolition of existing garages and the construction of car parking bays with associated works at Yew Close, Gurnos Estate, Merthyr Tydfil - Pricing Schedule for completion
Name of Bidder_______________________________
*Please complete the pricing table below, which will constitute your offer to deliver the works
*Costs are GBP and exclusive of VAT
*The following scope of works has been produced to provide an overall estimate of the necessary works to complete the project.
*Bidders must survey the site, verify all scope of works, identify any potential extras, and provide accurate final costs for the works, whether expressly included in the below schedules or not.
*Compensation events will only raised if there is significant unforeseen structural works that could not be identified.
*Rates are 'all-in' and must be inclusive of all materials, labour, prelim costs to deliver the requirements of MVH in line with the tender instructions, whether expressly included or not
*Where 'item is stated' the rates submitted must include for all identified properties
Item No | Area Heading | DESCRIPTION OF WORKS | Unit | Quantity - To be amended by contractor if required | Rate (£ ex VAT) | Total Cost (£ ex VAT) | Comments
a) Project information
1 |  | Location - Yew Close, Gurnos Estate, Merthyr Tydfil. | Info | Info
2 |  | Scope of works - Demolition of existing garages, site clearance, construction of new car parking bays with associated works. | Info | Info
3 |  | The contact person for site visits to inspect for quotation purposes is Nicholas Daley - Email: - Nick.Daley@mvhomes.org.uk | Info | Info
4 |  | This schedule of work is for pricing purpose and is not a guide to the sequence of work. The scope of works has been produced to provide an overall estimate of costs. The contractor must attend site, verify all scope of works, identify any potential extras, and provide accurate final estimated cost of works. Compensation events will only be raised if there is significant unforeseen works that could not be identified. | Info | Info
5 |  | All measurements and sizes indicated in this schedule of work and the accompanying drawings are for reference only – all measurements should be checked on site. Any discrepancies, inaccuracies etc found when carrying out the works must be reported to the project surveyor. | Info | Info
6 |  | A notice of intended demolition must be submitted to M.T.C.B.C local authority building control department a minimum of 6 weeks prior to commencement of any works. Additionally a Section 171 highway notice must also be submitted the local authority highways department prior to commencement. | Info | Info
7 |  | The Principal Contractor must liaise with the local authority engineering department regarding the SAB drainage design and installation on site. The Principal Contractor must pay all applicable fees. All SAB ducuments and information are porovided within tender pack. | Info | Info
8 |  | All demolition works must to be carried out in accordance with the Ecologists report that has been provided within the tender pack. Bird/Bat boxes must be installed prior to any works commencing - to be positioned as per report. | Info | Info
9 |  | Following the appointment of a Principal Contractor, all asbestos removal works will need to be arranged and co-ordinated between the Principle Contractor and M.V.H Project Surveyor and Asbestos Compliance Team prior to works commencing. Asbestos reports have been provided within the tender pack. | Info | Info
b) Preliminaries & Enabling Works
10 |  | Site Establishment Package to Include - Signage, PPE, Site Protection, First Aid, setup of a welfare and storage cabins. etc. Wash down and clear all areas on completion, leave site in clean condition on completion. | item | 1 | 0 | 0
11 |  | Health and Safety - This project is governed by the requirements of the Construction, Design and Management Regulations (CDM 2015) and the Principal Contractor shall include for all costs in discharging their duties and obligations as Principal Contractor. To include a full time Site manager. Allow for all additional costs incurred in complying with the requirements of current Health and Safety legislation. Additionally, comply in all respects with current British/European Standards and specifications, whether or not specifically stated in this schedule or not. | item | 1 | 0 | 0
12 |  | Carry out all pre-installation inspections/surveys specified by product manufacturer to ensure the existing ground is suitable to receive the proposed system and to ensure works comply with Building Regulations and British/European Standards. All works to be carried out strictly in accordance with the drawings/specifications provided and to the methods stated by the product manufacturers. | item | 1 | 0 | 0
13 |  | Provide, maintain and remove on completion temporary secure fencing to site. Provide adequate pedestrian safety barriers during course of works. Principal Contractor to ensure safety barriers are erected at all times. | item | 1 | 0 | 0
14 |  | Protect and maintain all utility apperratus, drains, gullies, etc. both within the site boundaries and those of the adjoining areas which may be affected by the works. | item | 1 | 0 | 0
15 |  | Allow for CAT scanning of whole site for services prior to commencing work on site. Care must be taken when excavating the area. | item | 1 | 0 | 0
16 |  | Allow for protecting the existing buildings, grounds, paths and site whilst the works are in progress. The Principal Contractor will be responsible for all damages and will be required to rectify any damage caused. | item | 1 | 0 | 0
17 |  | All materials and/or debris arising from the works, are to be carted away to a tip off-site provided at the Principal Contractor’s expense. Waste transfer notes must be provided. | item | 1 | 0 | 0
c) Demolition Works
18 |  | Demolition works to be carried out in accordance with the Ecologists report that has been provided. | Item | 1 | 0 | 0
19 |  | A Notice of Intended Demolition must be submitted to M.T.C.B.C local authority building control department a minimum of 6 weeks prior to commencement of any works. All fees need to br paid by Principal Contractor. | Item | 1 | 0 | 0
20 |  | Remove any remaining items/waste/debris from garages and cart away from site. | Item | 1 | 0 | 0
21 |  | Carefully remove flat roofs to the garages and cart away from site. | Item | 1 | 0 | 0
22 |  | Carefully remove garage doors and remove from site. | Item | 1 | 0 | 0
23 |  | Demolish walls, including dividing walls, supporting pillars, and boundary garden walls and remove all debris from site. | Item | 1 | 0 | 0
24 |  | Break up and grub up existing concrete floors and foundations and cart away - take care around the existing garden boundary walls. | Item | 1 | 0 | 0
25 |  | Break out existing concrete cross-overs and cart away all debris. | Item | 1 | 0 | 0
d) Construction Of boundary walls and Car Parking Bays
26 |  | The Principal Contractor must liaise with the local authority engineering department regarding the SAB drainage design and installation on site. Principal Contractor to pay all applicable fees as per the SAB Approval Notice provided. | item | 1 | 0 | 0
27 |  | Set out and excavate for new boundary wall foundations to area adjacent to No 40 Yew Close - as per structural engineers design provided. Allow for breaking out and reinstatement of concrete inside rear curtilage of number 40 Yew Close and all other reinstatement works. Remove debris from site. | item | 1 | 0 | 0
28 |  | Set out for new car parking area and excavate to reduce levels as per engineers design. Compact base well with a heavy duty compactor and remove all spoil off site. | item | 1 | 0 | 0
29 |  | All works must be in accordance with the engineers design and manufacturers instructions. | item | 1 | 0 | 0
30 |  | Pour new concrete foundations for boundary walls adjacent to number 40 Yew Close as per the structural engineers design and specification. | item | 1 | 0 | 0
31 |  | Construct new 215mm brickwork boundary wall as per the structural engineers design and specification provided. Engineering bricks to be used, colour to be agreed with client. | item | 1 | 0 | 0
32 |  | Allow for concrete edge restraint and kerb edges as required. | item | 1 | 0 | 0
33 |  | Lay sub-base to whole car parking area and allow for compaction to engineers design specification and Marshalls specifications - See drawings and specifications provided. | item | 1 | 0 | 0
34 |  | Lay dense bituminous macadam layer as per engineers design specification and Marshalls specification - Core drill 75mm holes at 750mm centres over entire area. Holes to be filled with material as per manufactures instructions. | item | 1 | 0 | 0
35 |  | Lay laying course as per engineers design specification and Marshalls manufacturers specification. | item | 1 | 0 | 0
36 |  | Supply and lay 80mm Marshalls Priora blocks - all to manufacturers instructions and recommendations. (colour to be agreed with client). | item | 1 | 0 | 0
37 |  | Joint with recommended open graded material - as per manufactures instructions and recommendations. | item | 1 | 0 | 0
38 |  | Allow for a contrasting colour block to demarcate individual parking bays - colour to be decided by client. | item | 1 | 0 | 0
39 |  | make good any damage to any surrounding areas. | item | 1 | 0 | 0
d) Drainage
40 |  | Principal Contractor must liaise with the local authority engineering department regarding the SAB drainage design and installation on site. Principal Contractor must arrange site inspections and pay all applicable fees. | item | 1 | 0 | 0
41 |  | Allow to create the drainage design as per the engineers drainage strategy SAB design. Drainage details and plans provided. | Item | 1 | 0 | 0
42 |  | Allow to create new chambers and make all new connections as per the design. Allow to make good to surrounding areas. | item | 1 | 0 | 0
e) Construction Of Crossover
43 |  | The contractor is responsible for liaising with the relevant local authority department with regards to the installation of the transition crossover from M.T.C.B.C owned land to M.V.H owned land. A Section 171 notice must be submitted to M.T.C.B.C Highways department prior to any works commencing. | item | 1 | 0 | 0
44 |  | Excavate and break out existing perimeter concrete, to include cross-overs and ramped areas and cart away all spoil. | item | 1 | 0 | 0
45 |  | lay additional sub base to all areas and compact well. | item | 1 | 0 | 0
46 |  | Allow for all necessary formwork and laying of 150mm concrete to all areas to ensure a smooth transition to new car parking bays. Make good to any damage to surrounding areas. | item | 1 | 0 | 0
47 |  | Allow for resetting any inspection chamber frames and covers/water stop tap to new levels. | Provisional Nr | 2 | 0 | 0
Lighting
48 |  | Install GemSun Vesper 10W, RAL7024 Light, 2700K, Sensor, Galv Metal Work 89mm, Optic 1. Light and post must be installed as per manufactures specification and installation instructions. Position of lights indicated on plans provided. Exact position and orientation to be agreed with client on site. Provide electrical certification if required. Contractor must Laise with the lighting manufacturers technical department on exact installation requirements. | item | x3 | 0 | 0
f) Bat and Bird Boxes
49 |  | The installation of bird boxes will need to be fixed prior to any works commencing onto the north east elevation of Plane Grove block of flats as per Ecologists report and biodiversity plan. The boxes will be grouped together and installed at a height of 5-7m, away from windows or doors with a clear flight path available. Boxes will be a woodcrete/Woodstone model (e.g., Vivara Pro Woodstone® Swift Nest Box or equivalent model) and surface mounted. See below info. https://www.nhbs.com/woodstone-swift-nest-box or https://www.wildlifeservices.uk/product-page/woodstone-swift-nest-box | Item | 1 | 0 | 0
[5 empty] | Sub-Total | 0
[5 empty] | Allow here for a 10% contingency | 0
[5 empty] | Total | 0