Appendix C

Specification of Requirements

Women’s Health and sexual health Needs assessments for Cardiff and Vale University Health Board

CAV-FTS-61145

Contents

1.	Background	2

2.	Requirement	4

3.	Service Levels & Performance	7

4.	Timeline	7

5.	Governance and Reporting Structure	8

6.	Risk Management and Mitigation	8

7.	Data Access and Permissions	8

8.	Ethical Considerations and Data Governance	9

## Background

In December 2024, the National Strategic Clinical Network for Women’s Health published the first ‘NHS Wales Women’s Health Plan’ (the Plan). The Plan is a ten-year vision (2025-2035) that outlines an NHS Wales approach to improving the health outcomes for women in Wales. Women's Health Plan for Wales launched - NHS Wales Performance and Improvement The 10-year plan has been two years in the making and follows the publication of the Welsh Government’s Quality Statement for Women’s and Girls’ Health in 2022. This made clear that approaches to healthcare need to change so women can access the care they need in a timely way; that the health service is responsive to their choices and needs and that research and development reflects women and girls’ lived experiences. It is an NHS Plan, which has been co-ordinated and led by the National Strategic Clinical Network for Women’s Health (the Women’s Health Network) with involvement from NHS staff, colleagues, experts in the field, and third sector organisations. It builds upon the work of the ‘Discovery Report’, which captured the voices of 4000 women and girls in Wales. The Plan will be delivered over ten years, through 64 short, medium and long– term actions. It will follow a life course approach, with a focus on delivery of services from 16 years of age, often an important time of transition within health services for girls. The Plan has 8 priority areas: - Menstrual Health - Endometriosis and Adenomyosis - Contraception, Post-Natal Contraception and Abortion Care - Preconception Health - Pelvic Health and Incontinence - Menopause - Violence Against Women, Domestic Abuse and Sexual Violence - Ageing Well and Long-term Conditions Across the Life Course The Plan outlines the key health inequalities experienced by women in Wales at a population level, and highlights some of the disparities in health that are emerging. It also highlights opportunities for closing the gender gap, improving health across our NHS services. The Plan will be delivered locally by the Cardiff and Vale University Health Board. A key requirement from the Women’s Health Plan for Wales is outlined below: “Scoping exercise to review current workforce capability and capacity to deliver specialist women's health 'hubs' in each Health Board to support timely diagnosis and management of menstrual health conditions, with a pathfinder established in each Health Board by the end of March 2026.” The priority areas for scoping the Women’s Health Hubs projects in Wales are three of the eight priorities within the Women’s Health Pla, and the main stages of a woman’s life course: - Priority 1 Menstrual Health (To include Endometriosis, Dysmenorrhea, Heavy Menstrual Bleeding, PMDD and PCOS). - Priority 3 Contraception, Post-natal Contraception and Abortion Care (To include preconception health, abortion care and initial fertility assessments). - Priority 6 Menopause (To include Premature Ovarian Insufficiency (POI), management of unscheduled bleeding on HRT and Testosterone).

## Requirement

The Requirement To support and complement the local delivery of the national Women’s Health Plan workstream, two Health Needs Assessments are required to ensure that the needs of our population are understood and addressed appropriately – a Sexual Health Needs Assessment, and a Women’s Health Needs Assessment. The two reports are closely linked and inter-dependent with regards to topics, key stakeholders and populations of interest. There will likely be overlap with regards to the production of the report (e.g. focus groups) and areas of discussion (e.g. contraception) which could create unnecessary duplication from two separate providers. However, due to the current service arrangements, it is required to have these two reports separately to allow all aspects of sexual health services to be reviewed, as recommendations on one element of the service would impact the whole service. Therefore, a single provider will be sought to produce both reports as outlined below. The awarded bidder will: - Be responsible for planning the HNA, engaging with stakeholders for the HNA, analysing all data for the HNA, reporting the findings of the HNA and planning for and managing risks associated with timely completion of the HNA - Participate and engage in regular (at least fortnightly) progress meetings with key stakeholders to outline and update on the progress of the HNA - Work with key stakeholder to agree the scope, data, key literature and priorities to create the reports - Provide regular updates to key stakeholders and promptly escalate any issues or challenges with the delivery of the reports - Produce annotated outlines, interim and final reports as per agreed timelines (see below) - Ensure they have developed a process by which to provide feedback from the HNA to stakeholders and those wider members of our communities who fed into the HNA. - Ensure all data collected for the HNA is handed over to C and V UHB and no data or part of the HNA is published or used by the bidder in the future, unless with the express permission of the UHB. The aim of the Health Needs Assessments will be to: - Understand the met and unmet needs of residents across Cardiff and the Vale of Glamorgan in relation to the 3 priority areas of the Women’s Health Plan for Wales, using a range of methodologies - Understand what services are currently being delivered for the defined population to address these - Assess the gaps in services in meeting the identified needs of the population - Develop evidence-based recommendations to support strategic planning to meet the needs of the local population, in alignment with local, regional and national priorities The scope of the two Health Needs Assessments are outlined below - Sexual health needs assessment (SHNA) - Sexual health outcomes, behaviours, and service usage in Cardiff and the Vale of Glamorgan - Access to contraception, Sexually Transmitted Infections (STI) testing and treatment, and sexual health education - Priority populations include - young people (under 25 years of age); - women of reproductive age (15-54 years old); - LGBTQ+ communities. - ethnic minority groups. - health inclusion groups including asylum seekers, those experiencing homelessness; those in contact with the criminal justice system; Gypsy, Roma and Traveller communities; those affected by sex work - people living in areas of high deprivation as described by the Welsh Index of Multiple Deprivation - Integration with broader public health initiatives (e.g. mental health, substance use, safeguarding, chemsex) - Women’s Health Needs assessment (WHNA) - The needs of the population and the current services addressing these around - Priority 1 Menstrual Health (To include Endometriosis, Dysmenorrhea, Heavy Menstrual Bleeding, PMDD and PCOS). - Priority 3 Contraception, Post-natal Contraception and Abortion Care (To include preconception health, abortion care and initial fertility assessments). - Priority 6 Menopause (To include Premature Ovarian Insufficiency (POI), management of unscheduled bleeding on HRT and Testosterone). The key stakeholders for both HNAs include (but are not limited to): - Cardiff and Vale University Health Board - General Practitioners and Primary Care - Public Health Wales - Cardiff Council and Vale of Glamorgan Council - Local schools, colleges and youth services - Community leaders and service users - Third sectors groups Additional stakeholders for the SHNA may include: - YMCA Cardiff, Terrence Higgins Trust Cymru, Brook Cymru - LGBTQ+ support groups - Fast Track Cardiff and Vale A range of local, regional and national data sources will be expected to be used to develop the two HNAs. Quantitative data sources will include demographic assessment of the population, epidemiological assessment of disease and conditions incidence and prevalence, local and national audit data, healthcare service utilisation, prescribing data, and relevant health outcome data. Qualitative data will include focus groups with relevant population groups as discussed with the stakeholder group; interviews with key service delivery professionals, online surveys of public and staff; particular focus on seeking qualitative data from under-represented groups. Literature reviews will be undertaken for both HNAs. This will identify the current evidence basis for the interventions and services which best meet the identified needs of the population. The literature reviews will need to encompass academic and ‘grey’ literature. A mixed methodology will be expected to be used, incorporating epidemiological, comparative and corporate health needs assessment approaches to ensure a comprehensive and robust analysis is undertaken. This will require: - Review of local and national data sets - Reviews of services offered elsewhere in Wales/UK with comparable population needs - Stakeholder engagement and feedback through online and in-person routes, including interviews, focus groups and surveys. This will be undertaken in partnership with third sector organisation separately commissioned as the local facilitator for patient and community engagement and co-production as part of the wider women’s health plan work locally - Collection and analysis of primary qualitative data related to this topic, to include gathering of information from both the general population, as well as a particular focus on seeking qualitative data from the groups listed above. - Expectation would be a minimum of two focus groups for each HNA and two surveys for each HNA - Literature and evidence review A key theme for both HNAs will be to understand the health inequalities experienced by different populations. This will need to be prominent within the data collection, analysis, presentation and final report production. Funding of up to £50,000.00 (including VAT) is available to develop the two Health Needs Assessments and deliver this work within 5 months of project initiation. The value of the contract will include all associated costs to the provider e.g. venue, accommodation and travel (if needed). It is anticipated this work can be delivered predominantly remotely. However some activities required in the production of this report e.g. qualitative data collection from focus groups may require in-person attendance. If the awarded bidder is within reasonable travel distance, there may be value in holding an initial project inception meeting or key stakeholder consultation in-person. Project phases include: - Project planning and initiation - Team and stakeholder coordination - Data collection and analysis - Rapid evidence review and review of relevant documentation - Key stakeholder engagement - Reporting and dissemination - Quality assurance - Final deliverable production Output Requirement - Draft annotated outline of both HNAs following project inception meeting with key stakeholders - GANTT chart outlining timelines for completion of the work - Interim advanced draft of the written content of the reports with sufficient time for stakeholder consultation (minimum 3 weeks) so that feedback can be incorporated into a final draft - Final draft of the written content with Executive Summary and references (using an agreed formal reference style), hyperlinks and proofreading for each report. - A presentation of the final report to stakeholders, with opportunity for questions and answers. - A prepared presentation and summary written report that is available for dissemination in easy read format to feedback and update wider stakeholders that have been involved in developing the HNAs

## Service Levels & Performance

The awarded bidder will be monitored against service levels and key performance indicators (KPIs) specified in the proposal and agreed prior to award of the contract. Service levels: - Annotated outline (5% of output) - Interim advanced draft of the report (45%) - Final report (55%) KPIs include: - High participation from diverse communities across Cardiff and the Vale of Glamorgan - Delivery of project inception meeting and regular progress meeting with key stakeholders - Annotate outline of the report in consultation with key stakeholders - Delivery of project inception meeting and regular progress meetings with key stakeholders - Annotated outline of the report in consultation with key stakeholders - Utilisation of a range of methods to ensure inclusion of all relevant documents, strategies, plans, activities, initiatives, campaigns, interventions inter alia in the report - Interim draft of the report and stakeholder consultation - Final written report containing all key sections including Executive Summary

## Timeline

An outline of key milestones and expected timescales for achieving phases is provided below. It is expected that some of these may run in parallel. Bidders can develop a more detailed timeline that would meet the objectives of the funding and demonstrate impact. Timeline will be requested within technical evaluation, with indicative milestones and programmed to be provided. Progress against the agreed timeline will be reviewed in regular meetings to be agreed between representative of the stakeholder group and provider. Project planning, initiation and team and stakeholder coordination; 2 weeks; Define scope, engage local stakeholders. Data collection; 6 – 8 weeks; Surveys, interviews, focus groups, stakeholder engagement. Rapid literature review; 4 weeks. Analysis and synthesis; 4 weeks; Analyse data, identify key findings. Reporting, final deliverable product and dissemination; 4 weeks; Draft and finalise report.

## Governance and Reporting Structure

The appointed provider will report into a steering group (one for each HNA), comprising of a number of key stakeholders (to include representatives from the UHB and wider partners). This steering group will also oversee the output of the work. A senior member of the Public Health Team of the Cardiff and Vale University Health Board will also act as a direct link for the work, should the appointed provider have any queries outside the steering group meetings.

## Risk Management and Mitigation

We would expect bidders to include a risk register or mitigation plan, to outline how they will be plan to avoid and respond to any potential risks related to the HNAs, to include data collection challenges or stakeholder engagement as part of their bid.

## Data Access and Permissions

The bidder would be expected to outline how they will manage any data provided to them, as part of the development of this HNA, to ensure that they are compliant with GDPR and wider information governance good practice. Where it is identified that health data (or any other sensitive data) may be needed to support this HNA, the appointed provider would be expected to discuss this with the steering group who will identify whether and how the appointed bidder should have access to and use this data.

## Ethical Considerations and Data Governance

The bidder would be expected to outline how they will manage any data provided to them, as part of the development of the HNAs, to ensure that they are compliant with GDPR and wider information governance good practice. Please detail any other frameworks or approaches your organisation takes to ensuring adequate consent processes, good safeguarding practice and any other approval / ethical policies you have in place that would be relevant to the development and undertaking of the HNAs.