## Tender Sum Analysis
Tender Sum Analysis - Sports Wales Changing Rooms
| Ref | Description |  | Total
Generally
Site Safety
| 1 | Main contractor's preliminaries |  | 0
| 2 | Demolitions |  | 0
| 3 | Alterations, Repairs and Conservation |  | 0
| 4 | Masonry |  | 0
| 5 | Proprietary linings and Partitions |  | 0
| 6 | General Joinery |  | 0
| 7 | Floor, Wall, Ceilings and Roof Finishes |  | 0
| 8 | Decorations |  | 0
| 9 | Suspended ceilings |  | 0
| 10 | FF&E |  | 0
| 11 | Drainage |  | 0
| 12 | MEP |  | 0
| 13 | Additional works |  | 0
|  | Sub Total |  | 0
|  | Main Contractor Overheads and profit | 0% | 0
Contingency
|  | Total to Form of Tender (excluding VAT) |  | 0

## General
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
General
0.01 | This document is a schedule of works intended to describe the content and scope of the works required. It has not been measured in strict accordance with SMM7 and or NRM and it is not intended that the works will be remeasured
0.02 | The Contractor will be deemed to have read the drawings and specifications together with this Schedule of Works and to have included within the tender all of the works described in all the documents or reasonably inferred by them. In addition, it is essential that the Contractor arranges a site visit prior to tendering for the works, to assist their pricing comprehensively
0.03 | This Schedule of Works is to be read in conjunction with: - The Drawings - The Specifications - Any other salient design information supplied. Provide for the requirements set out in the above documents, and all associated costs
0.04 | All Works and subsequent amendments to be in accordance with the Building Regulations, and all amendments are to be to the satisfaction of the CA. All materials and workmanship to be in accordance with the relevant current British Standards, Codes of Practice and relevant regulations. The works are to be designed and constructed to meet all applicable mandatory and statutory regulations. Any variance from the above conformity within the Tender information should be identified and brought to the attention of the Client and document originator without delay.
0.05 | All dimensions and drawings are as accurate as possible, but contractors are advised to check all dimensions, levels, etc. before commencement of work. The agent will accept no responsibility for the Principal Contractor’s failure to do this. Similar or alternative materials may only be used if they meet with the Local Authority approval and are approved in writing by the Client prior to their usage.
0.06 | The Principal Contractor shall be responsible for insurance for the works throughout the duration of the contract including public liability, fire, theft, and any damage caused by the Contractor throughout the duration of the contract. Insurance held by Principal Contractor to be in accordance with CA’s requirements. Contractor to provide evidence to CA within one week of request.
0.07 | Relevant statutory undertakers and service providers must be notified of any proposed works required. The Principal Contractor must ensure that all notices (e.g. Building Regulation inspection) are given as required and that all relevant licenses obtained, and relevant notices given (e.g. scaffolding, skips on the highway etc.) and that all safety barriers etc. are provided.
0.08 | The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
| Sub Total |  |  |  | 0

## Site Safety
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
Site Safety & Associated Provisions
0.01 | All sub-contractors are to be suitably qualified and experienced in working in the trades in which they are employed. All personnel to hold current CSCS cards and wear appropriate PPE. All plant operators to be suitably trained and hold appropriate IPAF or equivalent licenses.
0.02 | The Contractor is to ensure the works are priced to ensure there is no operational disruption to the surrounding neighbours.
0.03 | The Contractor is responsible for strict adherence to all site and Client rules and regulations.
0.04 | During the full period of the works the Contractor is to be aware and considerate of other users of the site. Suitable access and fire escape routes are always to be kept clear. Roads are always to be kept clear, noise is to be kept to a minimum, and hours of work to be between 8am and 5:30pm, Monday to Friday only unless agreed with Client in advance.
0.05 | Prior to the start of works a suitable area for use as a Contractors Compound is to be agreed with the CA and on-site storage, welfare facilities and site office is to be provided by the Principal Contractor for the duration of the works
0.06 | The Construction (Design & Management) Regulations 2015 (CDM) apply to this project and must be complied with
0.07 | Routes of all existing services within the vicinity of the proposed works to be determined before work commences.
| Sub Total |  |  |  | 0

## SOW - 1.0 Preliminaries
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
1 | Main contractor's preliminaries
1.2 | Main Contractor's cost items
1.2.1 | Management and staff
1.2.1.1 | Project specific management and staff
.1 | Project Manager / director - as required |  | wks |  | 0
.2 | Construction / Site Manager - as required |  | wks |  | 0
.3 | Supervisors, including works/trade package managers, building services engineering managers/co-ordinators and off-site production managers. |  | wks |  | 0
.4 | Health and safety manager/officers - as required |  | wks |  | 0
.5 | Commissioning manager (building engineering services). - as required |  | wks |  | 0
.6 | Planning/programming manager and staff - as required |  | wks |  | 0
.7 | Senior/managing quantity surveyor. - as required |  | wks |  | 0
.8 | Project/package quantity surveyors - as required |  | wks |  | 0
.9 | Procurement manager. - as required |  | wks |  | 0
.10 | Design manager. - as required |  | wks |  | 0
.11 | Project engineers. - as required |  | wks |  | 0
.12 | Environmental manager. - as required |  | wks |  | 0
.13 | Temporary works design engineers - as required |  | wks |  | 0
.14 | Materials management staff (e.g. storeman). - as required |  | wks |  | 0
.15 | Administrative staff, including secretary, document controllers, finance clerks and the like. - as required |  | wks |  | 0
.16 | Other management and staff - as required |  | wks |  | 0
1.2.1.2 | Visiting management and Staff - Not Covered by Contractors Overheads
.1 | Managing director, regional director, operations director, commercial director and the like. |  | wks |  | 0
.2 | Quality manager |  | wks |  | 0
.3 | Contracts/commercial manager |  | wks |  | 0
.4 | Health and safety manager. |  | wks |  | 0
.5 | Environmental manager/consultant |  | wks |  | 0
.6 | Other visiting management and staff. |  | wks |  | 0
0
1.2.1.3 | Extraordinary support Costs; allowance to include the following items as deemed required by the Contractor where not already included within Contractors Overheads; Legal advice costs; recruitment costs; team building costs; Other extraordinary support costs; Day Transport; Personnel transport (i.e. transportation of work operatives to site); Temporary Living accommodation; Subsistence Payment; out of normal hours working, including non-productive overtime allowances |  | item |  | 0
1.2.1.4 | Staff Travel |  | wks |  | 0
1.2.2 | Site Establishment
1.2.2.1 | Supply of Main Contractors Temporary site accommodation as required to deliver the Works to include the following as required
.1 | Offices |  | wks |  | 0
.2 | Meeting rooms |  | wks |  | 0
.3 | Canteens |  | wks |  | 0
.4 | drying rooms |  | wks |  | 0
.5 | Toilets and washrooms |  | wks |  | 0
.6 | First Aid room |  | wks |  | 0
.7 | Secure stores |  | wks |  | 0
.8 | Security office |  | wks |  | 0
.9 | Stairs |  | wks |  | 0
.11 | Delivery of temporary site accommodation to site, erection, construction and removal |  | item |  | 0
.12 | Land/property rental where site accommodation located off-site |  | wks |  | 0
.13 | Alterations and adaptations to site accommodation, including, partitioning, doors, painting and decorating, and the like. |  | item |  | 0
.14 | Relocation and alterations of temporary accommodation during construction stage |  | item |  | 0
.15 | Reinstating temporary site accommodation to original condition prior to removal from site |  | item |  | 0
.16 | Removal of site accommodation and temporary works in connection with site accommodation |  | item |  | 0
1.2.2.2 | Temporary Works in connection with Site establishment
.1 | Temporary bases and foundations for site accommodation, including maintenance and reinstatement of existing surfaces on completion of the works. |  | Item |  | 0
.2 | Connections to temporary service, including maintenance and removal on completion of the works. |  | Nr |  | 0
.3 | Connections to temporary drainage, in including maintenance and removal on completion of the works. |  | Nr |  | 0
.4 | Temporary site roads, paths and paving's (including on-site car parking), including reinstatement of existing surfaces on completion of the works |  | Item |  | 0
.5 | Temporary surface water drainage to temporary site roads, paths and pavements, including maintenance and removal on completion of the works. |  | Item |  | 0
1.2.2.3 | Furniture and equipment
.1 | General office furniture, including maintenance |  | item |  | 0
.2 | Conference/meeting room furniture, including maintenance |  | item |  | 0
.3 | Photocopiers, including purchase/rental, maintenance and other running costs |  | item |  | 0
.4 | Canteen furniture, including maintenance. |  | item |  | 0
.5 | Water dispensers, including purchase/rental, maintenance and other running costs. |  | Item |  | 0
.6 | Other office equipment, including maintenance |  | Item |  | 0
.7 | Removal of furniture and equipment |  | Item |  | 0
1.2.2.4 | IT Systems; including Computer hardware; installation, set up maintenance and running costs |  | Item |  | 0
1.2.2.5 | Consumables and services
.1 | Stationary |  | wks |  | 0
.2 | Computer and printer consumables |  | wks |  | 0
.3 | postage |  | wks |  | 0
.4 | Courier charges |  | wks |  | 0
.5 | Tea, coffee, water bottles and the like |  | wks |  | 0
.6 | First aid consumables |  | wks |  | 0
.7 | Photocopier consumables |  | wks |  | 0
.8 | Drawing printer consumables |  | wks |  | 0
1.2.2.6 | Brought-in services; Services outsourced by the main contractor such as; Catering; Equipment maintenance; document management; Printing; off-site parking; photographic services and the like |  | item |  | 0
1.2.2.7 | Sundries - as required
.1 | Main contractor’s signboards. |  | item |  | 0
.2 | Safety and information notice boards. |  | item |  | 0
.3 | Fire points. |  | item |  | 0
.4 | Shelters. |  | item |  | 0
.5 | Tool stores. |  | item |  | 0
.6 | Crane signage. |  | item |  | 0
1.2.3 | Site Temporary Services
1.2.3.1 | Temporary water supply
.1 | Temporary connections. |  | nr |  | 0
.2 | Distribution equipment, installation and adaptations |  | item |  | 0
.3 | Charges |  | wks |  | 0
1.2.3.2 | Temporary gas supply
.1 | Gas connection. |  | nr |  | 0
.2 | Distribution equipment, installation and adaptations |  | item |  | 0
.3 | Charges. |  | wks |  | 0
.4 | Bottled gas. |  | wks |  | 0
1.2.3.3 | Temporary electricity supply
.1 | Temporary connections |  | Nr |  | 0
.2 | Charges – power consumption for site establishment. |  | Wks |  | 0
.3 | Charges – power consumption for the works. |  | Wks |  | 0
.4 | Distribution equipment, installation and adaptations. |  | Item |  | 0
1.2.3.4 | Temporary telecommunication systems
.1 | Landlines (including connection and rental charges), including: – telephone and fax lines – ISDN lines. |  | Wks |  | 0
.2 | Mobile (cellular) phones, including: – mobile phones, including purchase or rental and connection charges. |  | Wks |  | 0
1.2.3.5 | Temporary drainage - As required
.1 | Temporary mains. |  | Item |  | 0
.2 | Septic tanks. |  | wks |  | 0
.3 | Sewage pumping |  | wks |  | 0
.4 | Distribution pipework, etc. |  | item |  | 0
.5 | Drainage installation and adaptations. |  | item |  | 0
.6 | Disposal charges (i.e. rates). |  | wks |  | 0
.7 | Disposal costs (i.e. tanker charges). |  | wks |  | 0
1.2.4 | Site Security
1.2.4.1 | Security Staff - if deemed required by the Contractor |  | wks |  | 0
1.2.4.3 | Hoardings, fences and gates; including gates; Doors; temporary works; decoration; modification; dismantling and removal and making good on completion |  | item |  | 0
1.2.5 | Safety and environmental protection
1.2.5.1 | Safety Programme; Works required to satisfy requirements of CDM Regulations
.1 | Safety audits |  | nr |  | 0
.2 | Staff safety training |  | item |  | 0
.3 | Notices and information to neighbours |  | item |  | 0
.4 | Personal protective equipment (PPE), including for employer and Site visitors |  | item |  | 0
.5 | Fire points |  | Nr |  | 0
.6 | Temporary fire alarms |  | Item |  | 0
.7 | Fire extinguishers. |  | Item |  | 0
.8 | Statutory safety signage |  | Item |  | 0
.9 | Traffic marshals - as deemed required by Contractor |  | Wks |  | 0
1.2.5.2 | Barriers and safety scaffolding
.1 | Guard rails and edge protection (e.g. to edges of suspended slabs and roofs). |  | item |  | 0
.2 | Temporary staircase balustrades (i.e. to new staircases during construction). |  | item |  | 0
.3 | Protection to holes and openings in ground floor slabs, suspended slabs and the like. |  | item |  | 0
.4 | Debris netting/plastic sheeting |  | item |  | 0
.5 | Fan protection. |  | item |  | 0
.6 | Scaffold inspections |  | item |  | 0
.7 | Protective walkways. |  | item |  | 0
.8 | Other safety measures. |  | item |  | 0
1.2.5.3 | Environmental protection measures - extent to be determined by Main Contractor
.1 | Control of pollution |  | item |  | 0
.2 | Residual control of noise |  | item |  | 0
.3 | Environmental monitoring. |  | item |  | 0
.4 | Environmental manager/consultant |  | item |  | 0
.5 | Environmental audits, including safety audits carried out by external consultant |  | Nr |  | 0
1.2.6 | Control and protection
1.2.6.1 | Survey, inspections and monitoring -
.1 | Surveys. |  | item |  | 0
.2 | Topographical survey. |  | item |  | 0
.3 | Non-employer dilapidation survey. |  | item |  | 0
.4 | Structural/dilapidations survey adjoining buildings. |  | item |  | 0
.5 | Environmental surveys. |  | item |  | 0
.6 | Movement monitoring. |  | item |  | 0
.7 | Maintenance and inspection costs |  | item |  | 0
1.2.6.2 | Setting out of the works |  | item |  | 0
1.2.6.3 | Protection of works
.1 | Protection of works and surrounding areas to project handover |  | item |  | 0
1.2.6.4 | Samples
.1 | Provision of samples; including Mock-ups and sample panels as required |  | item |  | 0
1.2.6.5 | Environmental control of building; including drying out; Temporary heating / cooling; temporary waterproofing (including over roofs as required); Temporary enclosures |  | item |  | 0
1.2.7 | Mechanical plant
1.2.7.3 | Cranage; including hire charges; operators; temporary works and bases; power and the like |  | item |  | 0
1.2.7.5 | Access plant; including delivery; collection; maintenance |  | item |  | 0
1.2.7.7 | Other Plant; Small plant and tools |  | item |  | 0
1.2.8 | Temporary works
1.2.8.1 | Access scaffolding
.1 | Provision for the design, installation; adaptions and removal of any Scaffolding for the works as required by the Main Contractor; |  | item |  | 0
1.2.8.2 | Temporary works
.1 | Provision for the design, installation; adaptions and removal of any Temporary Works as required by the Main Contractor to complete the Works; provision to include (but is not limited to); Support or propping; crash decks; temporary tree protection |  | item |  | 0
1.2.9 | Site records
.1 | Site records; Works records: – progress reporting. – site setting out drawings. – condition surveys and reports. – operation and maintenance manuals. – as-built/installed drawings and schedules. – co-ordinating, gathering and compiling health and safety information and presentation to CDM co-ordinator. – compilation of health and safety file (if required). |  | item |  | 0
1.2.10 | Completion and post-completion requirements
.2 | Handover; Training of building user’s staff in the operation and maintenance of the building engineering services systems; Provision of spare parts for maintenance of building engineering services.; Provision of tools and portable indicating instruments for the operation and maintenance of building engineering services systems; Pre-completion inspections; Final inspections. |  | item |  | 0
1.2.11 | Cleaning
.1 | Site tidy; Cleaning site accommodation – internal, including cleaning telephone handsets, other office furniture and equipment and window cleaning. |  | wks |  | 0
.2 | Waste management, including rubbish disposal (including compactor visits; skips and waste bins; roll-off, roll-on waste bins) and other disposal. |  | wks |  | 0
.3 | Maintenance of roads, paths and paving's; Maintenance of temporary site roads, paths, and pavements; Maintenance of public and private roads, including wheel spinners and road sweepers. |  | wks |  | 0
.4 | Building clean; Final builder’s clean. |  | item |  | 0
1.2.12 | Fees and charges
1.2.12.1 | Fees
.1 | Building control fees, where not paid by the employer |  | item |  | 0
.2 | Oversailing fees, |  | item |  | 0
.3 | Considerate Constructors’ Scheme fees (or alternative scheme operated by local authority). |  | item |  | 0
1.2.12.2 | Charges
.1 | Rates on temporary accommodation; if deemed required by Contractor |  | item |  | 0
.2 | Licences in connection with hoardings, scaffolding, gantries and the like. |  | item |  | 0
.3 | Licences in connection with crossovers, parking permits, parking bay suspensions and the like. |  | item |  | 0
1.2.13 | Site services
.1 | Temporary works that are not specific to an element; allowance to include (but is not limited too) temporary screens in connection with minor demolition ; supports to small openings cut into existing walls' temporary support for existing structures - all as deemed required by the Contractor |  | item |  | 0
1.2.13.2 | Multi-service gang
.1 | Site Labourer |  | wks |  | 0
.2 | Forklift / plant drivers as required |  | wks |  | 0
1.2.14 | Insurance, bonds, guarantees and warranties - as required by the Contract
.1 | Works insurance |  | item |  | 0
.2 | Public liability insurance |  | item |  | 0
.3 | Employer’s (main contractor’s) liability insurance |  | item |  | 0
.4 | Other insurances - as required by the Contract |  | item |  | 0
.5 | Other; Bonds; Guarantees and Warranties as required by the Contract |  | item |  | 0
| Sub Total |  |  |  | 0

## SOW - 2.0 Demolitions
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
2 | Demolitions
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
2.01 | 3 DEMOLITIONS Demolitions Existing Female Changing Room 1 Drawings ref: HLN-XX-00-DR-A-110011-S4-P01 Demolish existing masonry walls; dispose off site 140mm blockwork | 25 | m² | 0 | 0
2.02 | Existing Male Changing Room Drawings ref: HLN-XX-00-DR-A-110012 S4 P01 Demolish existing masonry walls; dispose off site 140mm blockwork | 36 | m² | 0 | 0
2.03 | Existing Female Changing Room 2 Drawings ref: HLN-XX-00-DR-A-110013 S4 P01 Demolish existing masonry walls; dispose off site 140mm blockwork | 24 | m² | 0 | 0
2.04 | Existing Female WC 2 Drawings ref: HLN-XX-00-DR-A-110014 S4 P01 Demolish existing masonry walls; dispose off site 140mm blockwork | 1 | m² | 0 | 0
2.05 | Existing Changing Room 6 Drawings ref: HLN-XX-00-DR-A-110015 S4 P01 Demolish existing masonry walls; dispose off site 140mm blockwork | 5 | m² | 0 | 0
| Sub Total |  |  |  | 0

## SOW - 3.0 Alterations, Repairs
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
3 | Alterations, Repairs and Conservation
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
3.01 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Female Changing Room 1 Drawing ref: HLN-XX-00-DR-A-110011-S4-P01 Fittings and fixtures Remove all existing fixtures and fittings, include of doors, benches, lockers, vanity units | 1 | item |  | 0
3.02 | Existing Male Changing Room Drawing ref: HLN-XX-00-DR-A-110012-S4-P01 Fittings and fixtures Remove all existing fixtures and fittings, include of doors, benches, lockers, vanity units | 1 | item |  | 0
3.03 | Existing Female Changing Room 2 Drawings ref: HLN-XX-00-DR-A-110013 S4 P01 Fittings and fixtures Remove all existing fixtures and fittings, include of doors, benches, lockers, vanity units | 1 | item |  | 0
3.04 | Existing Female WC 2 Drawings ref: HLN-XX-00-DR-A-110014 S4 P01 Fittings and fixtures Remove all existing fixtures and fittings, include of doors, benches, lockers, vanity units | 1 | item |  | 0
3.05 | Existing Changing Room 6 Drawings ref: HLN-XX-00-DR-A-110015 S4 P01 Fittings and fixtures Remove all existing fixtures and fittings, include of doors, benches, lockers, vanity units | 1 | item |  | 0
3.06 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Female Changing Room 1 Drawings ref: HLN-XX-00-DR-A-110011-S4-P01 Plumbing items or installations Mechanical installation; inclusive of Sanitaryware, Pipework, Mechanical ventilation and Above ground drainage and pipework; including making good structures disturbed | 1 | item |  | 0
3.07 | Electrical items or installations Electrical installation including making good structures disturbed | 1 | item |  | 0
3.08 | Finishes Ceramic wall tiling ; including preparing sub-base to receive new | 113 | m² |  | 0
3.09 | Suspended ceilings removing tiles, grid, suspension system, fittings and fixings | 34 | m² |  | 0
3.1 | Vinyl sheet flooring ; including preparing sub-base to receive new | 34 | m² |  | 0
3.11 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Male Changing Room Drawing ref: HLN-XX-00-DR-A-110012-S4-P01 Plumbing items or installations Mechanical installation; inclusive of Sanitaryware, Pipework, Mechanical ventilation and Above ground drainage and pipework; including making good structures disturbed | 1 | item |  | 0
3.12 | Electrical items or installations Electrical installation including making good structures disturbed | 1 | item |  | 0
3.13 | Finishes Ceramic wall tiling ; including preparing sub-base to receive new | 120 | m² |  | 0
3.14 | Suspended ceilings removing tiles, grid, suspension system, fittings and fixings | 39 | m² |  | 0
3.15 | Vinyl sheet flooring ; including preparing sub-base to receive new | 39 | m² |  | 0
3.16 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Female Changing Room 2 Drawings ref: HLN-XX-00-DR-A-110013 S4 P01 Plumbing items or installations Mechanical installation; inclusive of Sanitaryware, Pipework, Mechanical ventilation and Above ground drainage and pipework; including making good structures disturbed | 1 | item |  | 0
3.17 | Electrical items or installations Electrical installation including making good structures disturbed | 1 | item |  | 0
3.18 | Finishes Ceramic wall tiling ; including preparing sub-base to receive new | 110 | m² |  | 0
3.19 | Suspended ceilings removing tiles, grid, suspension system, fittings and fixings | 32 | m² |  | 0
3.2 | Vinyl sheet flooring ; including preparing sub-base to receive new | 32 | m² |  | 0
3.21 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Female WC 2 Drawings ref: HLN-XX-00-DR-A-110014 S4 P01 Plumbing items or installations Mechanical installation; inclusive of Sanitaryware, Pipework, Mechanical ventilation and Above ground drainage and pipework; including making good structures disturbed | 1 | item |  | 0
3.22 | Electrical items or installations Electrical installation including making good structures disturbed | 1 | item |  | 0
3.23 | Finishes Ceramic wall tiling ; including preparing sub-base to receive new | 36 | m² |  | 0
3.24 | Suspended ceilings removing tiles, grid, suspension system, fittings and fixings | 7 | m² |  | 0
3.25 | Vinyl sheet flooring ; including preparing sub-base to receive new | 7 | m² |  | 0
3.26 | 4 ALTERATIONS, REPAIRS AND CONSERVATION Alteration work to existing buildings Removing Existing Changing Room 6 Drawings ref: HLN-XX-00-DR-A-110015 S4 P01 Plumbing items or installations Mechanical installation; inclusive of Sanitaryware, Pipework, Mechanical ventilation and Above ground drainage and pipework; including making good structures disturbed | 1 | item |  | 0
3.27 | Electrical items or installations Electrical installation including making good structures disturbed | 1 | item |  | 0
3.28 | Finishes Ceramic wall tiling ; including preparing sub-base to receive new | 36 | m² |  | 0
3.29 | Suspended ceilings removing tiles, grid, suspension system, fittings and fixings | 17 | m² |  | 0
3.3 | Vinyl sheet flooring ; including preparing sub-base to receive new | 17 | m² |  | 0
| Sub Total |  |  |  | 0

## SOW - 4.0 Masonry
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
4 | Masonry
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
4.01 | 14 MASONRY Brick/block walling Lightweight concrete blocks; paint quality; in cement mortar (1:3); solid blocks compressive strength 7.0N/mm² Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Walls; half lap bond 100mm blockwork ; built against other work | 12 | m² |  | 0
4.02 | 14 MASONRY Brick/block walling Lightweight concrete blocks; paint quality; in cement mortar (1:3); solid blocks compressive strength 7.0N/mm² Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 100mm blockwork ; built against other work | 9 | m² |  | 0
4.03 | 14 MASONRY Brick/block walling Lightweight concrete blocks; paint quality; in cement mortar (1:3); solid blocks compressive strength 7.0N/mm² Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 100mm blockwork ; built against other work | 10 | m² |  | 0
4.04 | 14 MASONRY Brick/block walling Proprietary and individual spot items Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Wall connectors; stainless steel; fixing in accordance with manufacturer's instructions; subsequently building in ties as work proceeds 2.4m long, fixing to masonry backgrounds | 2 | nr |  | 0
4.05 | 14 MASONRY Brick/block walling Proprietary and individual spot items Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 2.4m long, fixing to masonry backgrounds | 3 | nr |  | 0
4.06 | 14 MASONRY Brick/block walling Proprietary and individual spot items Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 2.4m long, fixing to masonry backgrounds | 2 | nr |  | 0
| Sub Total |  |  |  | 0

## SOW - 5.0 Linings and Partition
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
5 | Proprietary linings and Partitions
The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
Forming and making good holes for ductwork and pipework in existing insulated metal cladding. 5 No 100mm dia pipes and 2 No 500 square ducts.
5.01 | 20 PROPRIETARY LININGS AND PARTITIONS Drylining and partitioning systems to walls and ceilings Proprietary linings Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 British Gypsum Gyproc Moisture resistant board, 12.5mm thick; self finished fixed to timber; Proprietary linings to ceilings, over 300mm wide on face | 10 | m² |  | 0
5.02 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 British Gypsum Gyproc Moisture resistant board, 12.5mm thick; self finished fixed to timber; Proprietary linings to ceilings, over 300mm wide on face | 21 | m² |  | 0
5.03 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 British Gypsum Gyproc Moisture resistant board, 12.5mm thick; self finished fixed to timber; Proprietary linings to ceilings, over 300mm wide on face | 10 | m² |  | 0
| Sub Total |  |  |  | 0

## SOW - 6.0 General Joinery
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
6 | General Joinery
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
6.01 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Duct panels, sanitary ware back panels and the like Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Proprietary panel duct and backing to sanitary ware by specialist supplied; including all support framing; waterproof membrane and necessary fixings to manufacturers specification IPS Frame colour: Polyrey Gris Orage G059 (RAL 7024 - LRV 0.09) IPS Panel colour: Polyrey Mousse M047 (PANTONE 624C - LRV 0.35) Cubicle Door colour: Polyrey Mousse M047 (PANTONE 624C - LRV 0.35) Cubicle Divider colour: Polyrey Gris Orage G059 (RAL 7024 - LRV 0.09) Voids: Where IPS are to be replaced, voids to match existing unless specified by Willis System guidance. To Accessible Toilet | 1 | nr |  | 0
6.02 | To Wash hand basin | 1 | nr |  | 0
6.03 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Duct panels, sanitary ware back panels and the like Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 To Accessible Toilet | 1 | nr |  | 0
6.04 | To Wash hand basin | 1 | nr |  | 0
6.05 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Duct panels, sanitary ware back panels and the like Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 To Accessible Toilet | 1 | nr |  | 0
6.06 | To Wash hand basin | 1 | nr |  | 0
6.07 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Duct panels, sanitary ware back panels and the like Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 To Accessible Toilet | 1 | nr |  | 0
6.08 | To Wash hand basin | 0 | nr |  | 0
6.09 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Duct panels, sanitary ware back panels and the like Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 To Accessible Toilet | 1 | nr |  | 0
6.1 | To Wash hand basin | 1 | nr |  | 0
6.11 | 22 GENERAL JOINERY Proprietary partitions, panels and cubicles Cubicle partition sets Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Plastic laminate covered Shower cubicle partitioning; aluminium fixings, trims to adjacent walls; supporting feet fixed to floor; matching doors including hinges and indicator bolts; matching fascias to exposed end of panels all as manufacturers specification Client to con?rm. Contractor to appoint manufacturer Sizing to Manufacturers sizes. HLN recommendations: o Full Height o Built in benching o Built in Dividing Partition o Colour ?nishes to match IPS colours o Fixtures and ?ttings to be appropriately sourced and installed to provide water resistance and anti-corrosion. Chrome ?nish or powder coated (Black) to match frame. Shower cubicles | 6 | nr |  | 0
6.12 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Plastic laminate covered Shower cubicle partitioning; aluminium fixings, trims to adjacent walls; supporting feet fixed to floor; matching doors including hinges and indicator bolts; matching fascias to exposed end of panels all as manufacturers specification Client to con?rm. Contractor to appoint manufacturer Sizing to Manufacturers sizes. HLN recommendations: o Full Height o Built in benching o Built in Dividing Partition o Colour ?nishes to match IPS colours o Fixtures and ?ttings to be appropriately sourced and installed to provide water resistance and anti-corrosion. Chrome ?nish or powder coated (Black) to match frame. Shower cubicles | 7 | nr |  | 0
6.13 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Plastic laminate covered Shower cubicle partitioning; aluminium fixings, trims to adjacent walls; supporting feet fixed to floor; matching doors including hinges and indicator bolts; matching fascias to exposed end of panels all as manufacturers specification Client to con?rm. Contractor to appoint manufacturer Sizing to Manufacturers sizes. HLN recommendations: o Full Height o Built in benching o Built in Dividing Partition o Colour ?nishes to match IPS colours o Fixtures and ?ttings to be appropriately sourced and installed to provide water resistance and anti-corrosion. Chrome ?nish or powder coated (Black) to match frame. Shower cubicles | 6 | nr |  | 0
6.14 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Plastic laminate covered Shower cubicle partitioning; aluminium fixings, trims to adjacent walls; supporting feet fixed to floor; matching doors including hinges and indicator bolts; matching fascias to exposed end of panels all as manufacturers specification Client to con?rm. Contractor to appoint manufacturer Sizing to Manufacturers sizes. HLN recommendations: o Full Height o Built in benching o Built in Dividing Partition o Colour ?nishes to match IPS colours o Fixtures and ?ttings to be appropriately sourced and installed to provide water resistance and anti-corrosion. Chrome ?nish or powder coated (Black) to match frame. Shower cubicles | 1 | nr |  | 0
6.15 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Plastic laminate covered Shower cubicle partitioning; aluminium fixings, trims to adjacent walls; supporting feet fixed to floor; matching doors including hinges and indicator bolts; matching fascias to exposed end of panels all as manufacturers specification Client to con?rm. Contractor to appoint manufacturer Sizing to Manufacturers sizes. HLN recommendations: o Full Height o Built in benching o Built in Dividing Partition o Colour ?nishes to match IPS colours o Fixtures and ?ttings to be appropriately sourced and installed to provide water resistance and anti-corrosion. Chrome ?nish or powder coated (Black) to match frame. Shower cubicles | 1 | nr |  | 0
6.16 | Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Internal doors Ply faced door paint grade; Kickplates to match existing; Pushplates to increase in length to protect the painted finish; New door handles; New deadlock and escutcheions and reuse the existing master series cylinder; Existing metal-louvered panels approx. 340mm x 340mm square, to be fitted to new doors; Architraves to be replaced like for like - softwood suitable for prime and painting; appropriate joint finishes to colour match tiling grouting or IPS colour finish; water and dirt repellent caulking | 3 | nr |  | 0
6.17 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Internal doors Ply faced door paint grade; Kickplates to match existing; Pushplates to increase in length to protect the painted finish; New door handles; New deadlock and escutcheions and reuse the existing master series cylinder; Existing metal-louvered panels approx. 340mm x 340mm square, to be fitted to new doors; Architraves to be replaced like for like - softwood suitable for prime and painting; appropriate joint finishes to colour match tiling grouting or IPS colour finish; water and dirt repellent caulking | 3 | nr |  | 0
6.18 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Internal doors Ply faced door paint grade; Kickplates to match existing; Pushplates to increase in length to protect the painted finish; New door handles; New deadlock and escutcheions and reuse the existing master series cylinder; Existing metal-louvered panels approx. 340mm x 340mm square, to be fitted to new doors; Architraves to be replaced like for like - softwood suitable for prime and painting; appropriate joint finishes to colour match tiling grouting or IPS colour finish; water and dirt repellent caulking | 3 | nr |  | 0
6.19 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Internal doors Ply faced door paint grade; Kickplates to match existing; Pushplates to increase in length to protect the painted finish; New door handles; New deadlock and escutcheions and reuse the existing master series cylinder; Existing metal-louvered panels approx. 340mm x 340mm square, to be fitted to new doors; Architraves to be replaced like for like - softwood suitable for prime and painting; appropriate joint finishes to colour match tiling grouting or IPS colour finish; water and dirt repellent caulking | 1 | nr |  | 0
6.2 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Internal doors Ply faced door paint grade; Kickplates to match existing; Pushplates to increase in length to protect the painted finish; New door handles; New deadlock and escutcheions and reuse the existing master series cylinder; Existing metal-louvered panels approx. 340mm x 340mm square, to be fitted to new doors; Architraves to be replaced like for like - softwood suitable for prime and painting; appropriate joint finishes to colour match tiling grouting or IPS colour finish; water and dirt repellent caulking | 1 | nr |  | 0
| Sub Total |  |  |  | 0

## SOW - 7.0 Finishes
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
7 | Floor, Wall, Ceilings and Roof Finishes
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
7.01 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Screed, beds and toppings Latex levelling screed; steel trowelled finish to receive floor covering 3mm thick; level; to concrete base >600mm wide; to falls, crossfalls and slopes not exceeding or equal to 15° from horizontal | 35 | m² |  | 0
7.02 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Screed, beds and toppings Latex levelling screed; steel trowelled finish to receive floor covering 3mm thick; level; to concrete base >600mm wide; to falls, crossfalls and slopes not exceeding or equal to 15° from horizontal | 44 | m² |  | 0
7.03 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Screed, beds and toppings Latex levelling screed; steel trowelled finish to receive floor covering 3mm thick; level; to concrete base >600mm wide; to falls, crossfalls and slopes not exceeding or equal to 15° from horizontal | 36 | m² |  | 0
7.04 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Screed, beds and toppings Latex levelling screed; steel trowelled finish to receive floor covering 3mm thick; level; to concrete base >600mm wide; to falls, crossfalls and slopes not exceeding or equal to 15° from horizontal | 47 | m² |  | 0
7.05 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Screed, beds and toppings Latex levelling screed; steel trowelled finish to receive floor covering 3mm thick; level; to concrete base >600mm wide; to falls, crossfalls and slopes not exceeding or equal to 15° from horizontal | 48 | m² |  | 0
7.06 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Vinyl sheet flooring; 2.00mm thick; welded seams; fixing with adhesive Finish to floors; cement and sand base > 600mm wide; Altro Aquaris Vole OR Altro Pisces Cuttlefish. Client to confirm | 35 | m² |  | 0
7.07 | Vinyl skirting Coved skirting; fixing with adhesive; bonded to flooring 150mm high; Inclusive of appropriate capping/joint to underside of tiling | 39 | m |  | 0
7.08 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Vinyl sheet flooring; 2.00mm thick; welded seams; fixing with adhesive Finish to floors; cement and sand base > 600mm wide; Altro Aquaris Vole OR Altro Pisces Cuttlefish. Client to confirm | 44 | m² |  | 0
7.09 | Vinyl skirting Coved skirting; fixing with adhesive; bonded to flooring 150mm high; Inclusive of appropriate capping/joint to underside of tiling | 44 | m |  | 0
7.1 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Vinyl sheet flooring; 2.00mm thick; welded seams; fixing with adhesive Finish to floors; cement and sand base > 600mm wide; Altro Aquaris Vole OR Altro Pisces Cuttlefish. Client to confirm | 36 | m² |  | 0
7.11 | Vinyl skirting Coved skirting; fixing with adhesive; bonded to flooring 150mm high; Inclusive of appropriate capping/joint to underside of tiling | 40 | m |  | 0
7.12 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Vinyl sheet flooring; 2.00mm thick; welded seams; fixing with adhesive Finish to floors; cement and sand base > 600mm wide; Altro Aquaris Vole OR Altro Pisces Cuttlefish. Client to confirm | 47 | m² |  | 0
7.13 | Vinyl skirting Coved skirting; fixing with adhesive; bonded to flooring 150mm high; Inclusive of appropriate capping/joint to underside of tiling | 34 | m |  | 0
7.14 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Vinyl sheet flooring; 2.00mm thick; welded seams; fixing with adhesive Finish to floors; cement and sand base > 600mm wide; Altro Aquaris Vole OR Altro Pisces Cuttlefish. Client to confirm | 48 | m² |  | 0
7.15 | Vinyl skirting Coved skirting; fixing with adhesive; bonded to flooring 150mm high; Inclusive of appropriate capping/joint to underside of tiling | 37 | m |  | 0
7.16 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Plaster; first coat, 11mm thick, cement:sand (1:3); second coat, 2mm thick, 'Thistle Multi-finish' plaster; steel smooth trowelled finish Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Finish to walls > 600mm wide | 93.6 | m² |  | 0
7.17 | Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Finish to Ceilings > 600mm wide | 10 | m² |  | 0
7.18 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Finish to walls > 600mm wide | 105.6 | m² |  | 0
7.19 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Finish to Ceilings > 600mm wide | 21 | m² |  | 0
7.2 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Finish to walls > 600mm wide | 96 | m² |  | 0
7.21 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Finish to Ceilings > 600mm wide | 10 | m² |  | 0
7.22 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Finish to walls > 600mm wide | 81.6 | m² |  | 0
7.23 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Finish to Ceilings > 600mm wide | 47 | m² |  | 0
7.24 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Finish to walls > 600mm wide | 88.8 | m² |  | 0
7.25 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Finish to Ceilings > 600mm wide | 0 | m² |  | 0
7.26 | 28 FLOOR, WALL, CEILING AND ROOF FINISHINGS Ceramic wall tiles; fixed with tile adhesive; flush pointed with tile grout; to plaster base Finish to walls Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Wall Finish Type 1 - Seven Green Matt Ceramic Wall Tile 1194x596x7mm; Ardex - Flex FS Grout (or Equivalent): Brilliant White - up to 4mm width (evenly spaced between tiles) | 23 | m² |  | 0
7.27 | Finish to walls Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Wall Finish Type 1 - Seven Green Matt Ceramic Wall Tile 1194x596x7mm; Ardex - Flex FS Grout (or Equivalent): Brilliant White - up to 4mm width (evenly spaced between tiles) | 50 | m² |  | 0
7.28 | Finish to walls Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Wall Finish Type 1 - Seven Green Matt Ceramic Wall Tile 1194x596x7mm; Ardex - Flex FS Grout (or Equivalent): Brilliant White - up to 4mm width (evenly spaced between tiles) | 29 | m² |  | 0
7.29 | Finish to walls Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Wall Finish Type 1 - Seven Green Matt Ceramic Wall Tile 1194x596x7mm; Ardex - Flex FS Grout (or Equivalent): Brilliant White - up to 4mm width (evenly spaced between tiles) | 21 | m² |  | 0
7.3 | Finish to walls Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Wall Finish Type 1 - Seven Green Matt Ceramic Wall Tile 1194x596x7mm; Ardex - Flex FS Grout (or Equivalent): Brilliant White - up to 4mm width (evenly spaced between tiles) | 21 | m² |  | 0
| Sub Total |  |  |  | 0

## SOW - 8.0 Decoration
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
8 | Decorations
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
8.01 | 29 DECORATION Painting and clear finishes INTERNAL WORK Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Painting plaster; prepare and apply one coat primer/sealer; emulsion paint; Dulux Trade Mouldshield; white; one mist coat emulsion paint, two full coats emulsion paint Shower areas; Eggshell Finish; exceeding 300mm girth | 10 | m² |  | 0
8.02 | General changing, Matt Finish; exceeding 300mm girth | 71 | m² |  | 0
8.03 | 29 DECORATION Painting and clear finishes INTERNAL WORK Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Shower areas; Eggshell Finish; exceeding 300mm girth | 21 | m² |  | 0
8.04 | General changing, Matt Finish; exceeding 300mm girth | 56 | m² |  | 0
8.05 | 29 DECORATION Painting and clear finishes INTERNAL WORK Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Shower areas; Eggshell Finish; exceeding 300mm girth | 10 | m² |  | 0
8.06 | General changing, Matt Finish; exceeding 300mm girth | 67 | m² |  | 0
8.07 | 29 DECORATION Painting and clear finishes INTERNAL WORK Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Shower areas; Eggshell Finish; exceeding 300mm girth | 0 | m² |  | 0
8.08 | General changing, Matt Finish; exceeding 300mm girth | 61 | m² |  | 0
8.09 | 29 DECORATION Painting and clear finishes INTERNAL WORK Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Shower areas; Eggshell Finish; exceeding 300mm girth | 0 | m² |  | 0
8.1 | General changing, Matt Finish; exceeding 300mm girth | 68 | m² |  | 0
| Sub Total |  |  |  | 0

## SOW - 9.0 Suspended Ceilings
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
9 | Suspended ceilings
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
9.01 | 30 SUSPENDED CEILINGS Demountable suspended ceilings Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Suspended ceiling; exposed metal grid metal suspended grid; 24mm white wide exposed grid; primary channels at 600mm centres; wire hangers; clips; nut and bolt connection 600 x 600mm British Gypsum Gyrex Bio 600 Ceilings; depth of suspension 150 - 500mm | 25 | m² |  | 0
9.02 | 30 SUSPENDED CEILINGS Demountable suspended ceilings Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Ceilings; depth of suspension 150 - 500mm | 22 | m² |  | 0
9.03 | 30 SUSPENDED CEILINGS Demountable suspended ceilings Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Ceilings; depth of suspension 150 - 500mm | 26 | m² |  | 0
9.04 | 30 SUSPENDED CEILINGS Demountable suspended ceilings Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Ceilings; depth of suspension 150 - 500mm | 47 | m² |  | 0
9.05 | 30 SUSPENDED CEILINGS Demountable suspended ceilings Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Ceilings; depth of suspension 150 - 500mm | 48 | m² |  | 0
| Sub Total |  |  |  | 0

## SOW - 10.0 FF&E
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
10 | FF&E
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
10.01 | 32 FURNITURE, FITTINGS AND EQUIPMENT General fixtures, furnishings and equipment Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Bespoke Joinery; Five-at-Heart Systems (FFL to U/S Ceiling) Towel Station | 1 | item |  | 0
10.02 | Five-Pandora Lockers | 1 | item |  | 0
10.03 | Accessible Lockers | 1 | item |  | 0
10.04 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Sanitary Accessories - Client Supplied TBC Sanitary Bin | 1 | nr |  | 0
10.05 | Soap Dispenser | 1 | nr |  | 0
10.06 | Towel Dispenser | 1 | nr |  | 0
10.07 | Waste Bin | 1 | nr |  | 0
10.08 | Mirror | 1 | nr |  | 0
10.09 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; assembling and screw fixing to backgrounds requiring plugging Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Sanitaryware Taps - Non-concussive Toca L20 XL Handle Basin Mixer - Black | 2 | nr |  | 0
10.1 | Basin - Roca FINECERAMIC Countertop 425mm dia - Matt white | 2 | nr |  | 0
10.11 | Ideal spec - Part M Silk Black (Left-Hand S1245(XG) or Right-Hand S1246(XG)) | 1 | nr |  | 0
10.12 | HEWI Shower Unit - Shower Head - Grab Rails - Wall-Mounted Back Rest - Curtain Track | 1 | nr |  | 0
10.13 | Showers - Delabie sporting 2 manual push button - time flow shower panel - 714700 | 5 | nr |  | 0
10.14 | 32 FURNITURE, FITTINGS AND EQUIPMENT General fixtures, furnishings and equipment Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Bespoke Joinery; Five-at-Heart Systems (FFL to U/S Ceiling) Towel Station | 1 | item |  | 0
10.15 | Five-Pandora Lockers | 1 | item |  | 0
10.16 | Accessible Lockers | 1 | item |  | 0
10.17 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Sanitary Accessories - Client Supplied TBC Sanitary Bin | 1 | nr |  | 0
10.18 | Soap Dispenser | 1 | nr |  | 0
10.19 | Towel Dispenser | 1 | nr |  | 0
10.2 | Waste Bin | 1 | nr |  | 0
10.21 | Mirror | 1 | nr |  | 0
10.22 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; assembling and screw fixing to backgrounds requiring plugging Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Sanitaryware Taps - Non-concussive Toca L20 XL Handle Basin Mixer - Black | 2 | nr |  | 0
10.23 | Basin - Roca FINECERAMIC Countertop 425mm dia - Matt white | 2 | nr |  | 0
10.24 | Ideal spec - Part M Silk Black (Left-Hand S1245(XG) or Right-Hand S1246(XG)) | 1 | nr |  | 0
10.25 | HEWI Shower Unit - Shower Head - Grab Rails - Wall-Mounted Back Rest - Curtain Track | 1 | nr |  | 0
10.26 | Showers - Delabie sporting 2 manual push button - time flow shower panel - 714700 | 6 | nr |  | 0
10.27 | 32 FURNITURE, FITTINGS AND EQUIPMENT General fixtures, furnishings and equipment Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Bespoke Joinery; Five-at-Heart Systems (FFL to U/S Ceiling) Towel Station | 1 | item |  | 0
10.28 | Five-Pandora Lockers | 1 | item |  | 0
10.29 | Accessible Lockers | 1 | item |  | 0
10.3 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Sanitary Accessories - Client Supplied TBC Sanitary Bin | 1 | nr |  | 0
10.31 | Soap Dispenser | 1 | nr |  | 0
10.32 | Towel Dispenser | 1 | nr |  | 0
10.33 | Waste Bin | 1 | nr |  | 0
10.34 | Mirror | 1 | nr |  | 0
10.35 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; assembling and screw fixing to backgrounds requiring plugging Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Sanitaryware Taps - Non-concussive Toca L20 XL Handle Basin Mixer - Black | 1 | nr |  | 0
10.36 | Basin - Roca FINECERAMIC Countertop 425mm dia - Matt white | 1 | nr |  | 0
10.37 | Ideal spec - Part M Silk Black (Left-Hand S1245(XG) or Right-Hand S1246(XG)) | 1 | nr |  | 0
10.38 | HEWI Shower Unit - SHower Head - Grab Rails - Wall-Mounted Back Rest - Curtain Track | 1 | nr |  | 0
10.39 | Showers - Delabie sporting 2 manual push button - time flow shower panel - 714700 | 5 | nr |  | 0
10.4 | 32 FURNITURE, FITTINGS AND EQUIPMENT General fixtures, furnishings and equipment Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Bespoke Joinery; Five-at-Heart Systems (FFL to U/S Ceiling) Towel Station | 1 | item |  | 0
10.41 | Five-Pandora Lockers | 1 | item |  | 0
10.42 | Accessible Lockers | 1 | item |  | 0
10.43 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Sanitary Accessories - Client Supplied TBC Sanitary Bin | 1 | nr |  | 0
10.44 | Soap Dispenser | 1 | nr |  | 0
10.45 | Towel Dispenser | 1 | nr |  | 0
10.46 | Waste Bin | 1 | nr |  | 0
10.47 | Mirror | 1 | nr |  | 0
10.48 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; assembling and screw fixing to backgrounds requiring plugging Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Sanitaryware Taps - Non-concussive Toca L20 XL Handle Basin Mixer - Black | 0 | nr |  | 0
10.49 | Basin - Roca FINECERAMIC Countertop 425mm dia - Matt white | 0 | nr |  | 0
10.5 | Ideal spec - Part M Silk Black (Left-Hand S1245(XG) or Right-Hand S1246(XG)) | 1 | nr |  | 0
10.51 | HEWI Shower Unit - SHower Head - Grab Rails - Wall-Mounted Back Rest - Curtain Track | 1 | nr |  | 0
10.52 | 32 FURNITURE, FITTINGS AND EQUIPMENT General fixtures, furnishings and equipment Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Bespoke Joinery; Five-at-Heart Systems (FFL to U/S Ceiling) Towel Station |  | item |  | 0
10.53 | Five-Pandora Lockers |  | item |  | 0
10.54 | Accessible Lockers |  | item |  | 0
10.55 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Sanitary Accessories - Client Supplied TBC Sanitary Bin | 1 | nr |  | 0
10.56 | Soap Dispenser | 1 | nr |  | 0
10.57 | Towel Dispenser | 1 | nr |  | 0
10.58 | Waste Bin | 1 | nr |  | 0
10.59 | Mirror | 1 | nr |  | 0
10.6 | 32 FURNITURE, FITTINGS AND EQUIPMENT Sanitary appliances and fittings Sanitary fittings by stated supplier; assembling and screw fixing to backgrounds requiring plugging Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Sanitaryware Taps - Non-concussive Toca L20 XL Handle Basin Mixer - Black | 0 | nr |  | 0
10.61 | Basin - Roca FINECERAMIC Countertop 425mm dia - Matt white | 0 | nr |  | 0
10.62 | Ideal spec - Part M Silk Black (Left-Hand S1245(XG) or Right-Hand S1246(XG)) | 1 | nr |  | 0
10.63 | HEWI Shower Unit - SHower Head - Grab Rails - Wall-Mounted Back Rest - Curtain Track | 1 | nr |  | 0
| Sub Total |  |  |  | 0

## SOW - 11.0 Drainage
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
11 | Drainage
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
11.01 | 33 DRAINAGE ABOVE GROUND Foul drainage installations Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 S3 P02 HLN-XX-ZZ-DR-A-230001 S4 P01 Pipework ancillaries Replace Floor gulley; P trap; mounting plate and flush grating; fixed into pipework including any alterations required | 3 | nr |  | 0
11.02 | 33 DRAINAGE ABOVE GROUND Foul drainage installations Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Pipework ancillaries Replace Floor gulley; P trap; mounting plate and flush grating; fixed into pipework including any alterations required | 4 | nr |  | 0
11.03 | Allow for new floor gullies to shower areas, including and additional pipe work and making good as required | 7 | nr |  | 0
11.04 | 33 DRAINAGE ABOVE GROUND Foul drainage installations Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Pipework ancillaries Replace Floor gulley; P trap; mounting plate and flush grating; fixed into pipework including any alterations required | 2 | nr |  | 0
11.05 | 33 DRAINAGE ABOVE GROUND Foul drainage installations Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Pipework ancillaries Allow for new floor gullies to shower areas, including and additional pipe work and making good as required | 1 | nr |  | 0
11.06 | 33 DRAINAGE ABOVE GROUND Foul drainage installations Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Pipework ancillaries Allow for new floor gullies to shower areas, including and additional pipe work and making good as required | 1 | nr |  | 0
| Sub Total |  |  |  | 0

## SOW - 12.0 MEP
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
12 | MEP
The Tender is to be priced based on the information provided by the Drawings and Specifications. The Pricing Schedules are given for guidance purposes only and may not contain all of the intended works nor the full descriptions of all works and it remains the Contractors responsibility for any accuracy and sufficiency. The Contractor shall enter quantities and prices and insert any descriptions and quantities that he considers to have not yet been included. The quantities will not be subject to re-measure and the price will be tendered as a “Lump Sum” basis.
12.01 | Female Changing Room Drawings refs: HLN-XX-00-DR-A-210001 HLN-XX-XX-DR-A-220001 HLN-XX-ZZ-DR-A-230001 HLN-XX-00-DR-A-240001 Mechanical installation | 1 | Item |  | 0
12.02 | Electrical installation | 1 | Item |  | 0
12.03 | BWIC | 1 | Item |  | 0
12.04 | Gender Neutral Changing Drawings refs: HLN-XX-00-DR-A-210002 HLN-XX-XX-DR-A-220002 HLN-XX-ZZ-DR-A-230002 HLN-XX-00-DR-A-240002 Mechanical installation | 1 | Item |  | 0
12.05 | Electrical installation | 1 | Item |  | 0
12.06 | BWIC | 1 | Item |  | 0
12.07 | Male Changing Room Drawings refs: HLN-XX-00-DR-A-210003 HLN-XX-XX-DR-A-220003 HLN-XX-ZZ-DR-A-230003 HLN-XX-00-DR-A-240003 Mechanical installation | 1 | Item |  | 0
12.08 | Electrical installation | 1 | Item |  | 0
12.09 | BWIC | 1 | Item |  | 0
12.1 | Family Changing Room 1 Drawings refs: HLN-XX-00-DR-A-210004 HLN-XX-XX-DR-A-220004 HLN-XX-ZZ-DR-A-230004 HLN-XX-00-DR-A-240004 Mechanical installation | 1 | Item |  | 0
12.11 | Electrical installation | 1 | Item |  | 0
12.12 | BWIC | 1 | Item |  | 0
12.13 | Family Changing Room 2 Drawings refs: HLN-XX-00-DR-A-210005 HLN-XX-XX-DR-A-220005 HLN-XX-ZZ-DR-A-230005 HLN-XX-00-DR-A-240005 Pipework ancillaries Mechanical installation | 1 | Item |  | 0
12.14 | Electrical installation | 1 | Item |  | 0
12.15 | BWIC | 1 | Item |  | 0
| Sub Total |  |  |  | 0

## SOW - 13.0 Additional works
Tender Sum Analysis - Sports Wales Changing Rooms
Ref | Description | Qty | Unit | Rate | Total | Notes
13 | Additional works
| Sub Total |  |  |  | 0