Environment, Roads & Facilities

Infrastructure (Consultancy)

ERCF2509N 20

Pont Gell, Llangernyw

Volume 2 - Contract Data & Quality Questionnaire

June 2026

G.B. Edwards BEng (Hons) CEng FICE

Head of Environment, Roads & Facilities,

PO. Box 1, Colwyn Bay, LL29 0GG

01492 575337

affch@conwy.gov.uk / erf@conwy.gov.uk

Issue and Revision Record

| Document Title | Volume 2 - Contract Data & Quality Questionnaire - |
| --- | --- |
| Version | V1 |
| Status | Tender Issue |
| Filename | ERCF2509N 20 Pont Gell - Volume 2 – CD.docx |

| Revision | Notes | Date |
| --- | --- | --- |
| V1 | Tender Issue | 12/06/2026 |

|  | Signature | Name | Date |
| --- | --- | --- | --- |
| Prepared by | GRJ | Gerallt James | 12/06/2026 |
| Checked By |  | John Castle | 12/06/2026 |
| Approved by | BS | Bryn Shiland | 12/06/2026 |

Contents

Contract Data	5

The Client’s Contract Data	5

The Contractor’s Contract Data	9

The Contractor’s Offer and	10

Client’s Acceptance	10

Price List	11

Scope	15

Site Information	19

Freedom of Information Act 2000 Declaration	20

Anti-Collusion Certificate	21

Declaration	22

Appendix 1 - Quality Questionnaire	23

Engineering and Construction

Short Contract

| A contract between | Conwy County Borough Council |
| --- | --- |

| and |  |
| --- | --- |

| for | Pont Gell, Llangernyw |
| --- | --- |

Contract Forms

Contract Data

The Contractor’s Offer and Client’s Acceptance

Price List

Scope

Site Information

# Contract Data

## The Client’s Contract Data

The Client is

| Name | Conwy County Borough Council |
| --- | --- |
| Address for communications | PO Box 1, Colwyn Bay, LL29 0GG |

| Address for electronic communications | gerallt.james@conwy.gov.uk |
| --- | --- |

| The works are | Box Culvert Replacement |
| --- | --- |

| The site is | NGR 285165, 369470 See Location Plan - Drawing no ERCF2509 20 T101 |
| --- | --- |

| The starting date is | 07/09/2026 |
| --- | --- |

| The completion date is | 16/10/2026 |
| --- | --- |

| The delay damages are | £100 | per day |
| --- | --- | --- |

z

| The period for reply is | 1 | weeks |
| --- | --- | --- |

| The defects date is | 52 | weeks after Completion |
| --- | --- | --- |

| The defect correction period is | 4 | weeks |
| --- | --- | --- |

| The assessment day is the | Last Friday | of each month |
| --- | --- | --- |

| The retention is | 5 | % |
| --- | --- | --- |

The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does/does not apply

(delete as applicable)

The Adjudicator is

| Name |  |
| --- | --- |

| Address for communications |  |
| --- | --- |

| Address for electronic communications |  |
| --- | --- |

Contract Data

The Client’s Contract Data

| The interest rate on late payment is |  | % per complete week of delay. |
| --- | --- | --- |

Insert a rate only if a rate less than 0.5% per week of delay has been agreed.

| The Client provides this insurance | N/A |
| --- | --- |

Only enter details here if the Client is to provide insurance.

| The minimum amount of |  |
| --- | --- |
| cover for the third insurance |  |
| stated in the Insurance Table is, |  |
| for any one event |  |

| The minimum amount of |  |
| --- | --- |
| cover for the fourth insurance |  |
| stated in the Insurance Table |  |
| is, for any one event |  |

Is the Contractor’s obligation for design to use the skill and care normally used by professionals designing works similar to the works? Yes / No (delete as applicable)

The Contractor provides the following insurance cover

| Insurance against | Minimum amount of cover | Period following Completion or earlier termination |
| --- | --- | --- |
| Liability of the Contractor for claims made against it arising out of its failure to use the skill and care normally used by professionals designing works similar to the works | N/A | N/A |
|  | in respect of each claim, without limit to the number of claims |  |

Contract Data

The Client’s Contract Data

| For any one event, the liability |  |
| --- | --- |
| of the Contractor to the Client |  |
| for loss of or damage to the |  |
| Client’s property is limited to | £250,000 |

| The Contractor’s total liability |  |
| --- | --- |
| to the Client which arises |  |
| under or in connection with |  |
| the contract is limited to | £10,000,000 |

| The Adjudicator nominating |  |
| --- | --- |
| body is | Institution of Civil Engineers |

| The tribunal is | Courts |
| --- | --- |

| If the tribunal is arbitration, the |  |
| --- | --- |
| arbitration procedure is |  |

The conditions of contract are the NEC4 Engineering and Construction Short Contract June 2017 (with amendments January 2023) and the following additional conditions

Option Z1 – Corrupt Practices The Contractor has warranted that he has not committed any Prohibited Act and he does not do any of the Prohibited Acts. The Contractor does not: - offer to give to any person in the service of the Client any gift or consideration of any kind as an inducement or reward in relation to the obtaining or execution of this contract or any other contract with the Client or for showing favour or disfavour to any person in relation to this contract or any other contract with the Client, or - enter into this contract or any other contract with the Client if, in connection with this contract or any such other contract, commission has been paid or an agreement for the payment of commission has been made by him or on his behalf or to his knowledge, in accordance with the terms of the Bribery Act 2010. Option Z2 – Fair Wages and Conditions of Labour The Contractor shall in respect of all persons employed by him (whether in execution of the contract or otherwise) in every factory, workshop or place occupied or used by him for the execution of the contract comply with the following conditions, namely: - Pay rates of wages and observe hours and conditions of labour not less favourable than those established, for the trade or industry in the district where the work is carried out. The Contractor shall recognise the right of his work people to be members of such trade unions as they may choose or subject to Section 58 of the Employment Protection (Consolidation) Act 1978, as amended, not to be members of a trade union or other organisation of workers or to refuse to be a member of any particular trade union in other organisation of workers. The Contractor shall at all times during the continuance of the contract display, for the information of his work people in every factory, workshop or place occupied or used by him for the execution of the contract a copy of Clause (a) and (b) above. The Contractor shall be responsible for the observance of this clause by sub-contractors employed in the execution of the contract, and shall if required notify the County Borough Council of the names and addresses of all such sub-contractors. In the event of any question arising as to whether the foregoing conditions are being observed, the question shall, if not otherwise disposed of, be referred for decision to an independent arbitrator jointly agreed by the County Borough Council and the Contractor. The Contractor shall keep proper books and time sheets in relation to wages paid to persons in his employ and engaged in the execution of the contract, and such document shall, if required by the County Borough Council, be produced for inspection by any officer so authorised by the County Borough Council. Option Z3 – Prevention of Canvassing - The Contractor, by submitting his tender, confirms that he has not canvassed or solicited now or in the future any Member, Officer or Employee of the Council in connection with the award of this or any other tender or proposed tender for the Council and that no person employed by him or acting on his behalf has done any such act - Any breach of this Clause will entitle the Council to reject a tender and/or cancel a contract. Option Z4 – Equality and Diversity The Client is committed to the active promotion of equality and to valuing diversity in all its work. It is committed to honouring the duties and rights enshrined in legislation and where possible, will go further than the requirements of law. The Client believes that promoting diversity and equality of opportunity among its work force and more widely, will assist in meeting the needs and aspirations of the people of Wales. The Client therefore seeks to contract with companies with similar aspirations and this is reflected in the consideration of the Quality submissions made by tendering companies. Option Z5 – VAT Invoice The Contractor shall submit a valid VAT invoice, for the amount stated upon the payment certificate, to the Client within a maximum of 24 hours of being requested of such or at any time as requested by the Client Option Z6 – Procurement - During the tender period the Contractor shall establish that products named in the document for inclusion in the works are available within the programmed contract period. Should this not be the case the Contractor should put forward products of equivalent specification, which will be available within the contract period, in the tender submission for consideration.

Contract Data

## The Contractor’s Contract Data

The Contractor is

| Name |  |
| --- | --- |
| Address for communications |  |

| Address for electronic communications |  |
| --- | --- |

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are

| category of person | unit | rate |
| --- | --- | --- |

| Contracts Manager | Per Hour |  |
| --- | --- | --- |

| Site Manager | Per Hour |  |
| --- | --- | --- |

| Foreman | Per Hour |  |
| --- | --- | --- |

| Plant Operative | Per Hour |  |
| --- | --- | --- |

| Skilled Labour | Per Hour |  |
| --- | --- | --- |

| Labourer | Per Hour |  |
| --- | --- | --- |

| The published list of Equipment is | CECA (latest version) |
| --- | --- |

| The percentage for adjustment for Equipment is |  | % (state plus |
| --- | --- | --- |
|  |  | or minus) |

## The Contractor’s Offer and ## Client’s Acceptance

The Contractor offers to Provide the Works in accordance with these conditions of contract for an amount to be determined in accordance with these conditions of contract.

| The offered total of the Prices is |  |
| --- | --- |

Enter the total of the Prices from the Price List.

Signed on behalf of the Contractor

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

The Client accepts the Contractor’s Offer to Provide the Works

Signed on behalf of the Client

| Name |  |
| --- | --- |

| Position |  |
| --- | --- |

| Signature |  |
| --- | --- |

| Date |  |
| --- | --- |

## Price List

| Item no. | Description | Unit | Quantity | Rate | Price |
| --- | --- | --- | --- | --- | --- |
|  | GC 990/MMHW - Contractors Preliminaries |  |  |  |  |
| 990.1 | Establishment of temporary accommodation and equipment for the Contractor | Item | 1 |  |  |
| 990.2 | Servicing of temporary accommodation and equipment for the Contractor | Wk | 6 |  |  |
| 990.3 | Removal of temporary accommodation and equipment for the Contractor | Item | 1 |  |  |
| 990.4 | Supply, erect and take down temporary over pumping of existing river | Item | 1 |  |  |
| 990.5 | Maintenance of over pumping for use by the Contractor | Wk | 6 |  |  |
|  | GC 106/MMHW - Working on the highway |  |  |  |  |
| 106.1 | Temporary management for all works | Item | 1 |  |  |
| 106.2 | Establishment of closure of Unclassified Road | Item | 1 |  |  |
| 106.3 | Maintenance and adjustment for closure of Road | Day | 39 |  |  |
| 106.4 | Removal of closure of Unclassified Road | Item | 1 |  |  |
| 106.5 | Establishment of temporary diversion routes for traffic at Unclassified Road | Item | 1 |  |  |
| 106.6 | Maintenance of temporary diversion routes for traffic at Unclassified Road | Day | 39 |  |  |
| 106.7 | Removal of temporary diversion routes for traffic at Plas Unclassified Road | Item | 1 |  |  |
|  | GC 109/MMHW - Site preparation and Clearance |  |  |  |  |
| 109.1 | General site clearance | ha | 0.05 |  |  |
| 109.2 | General site clearance of Vegetation | m² | 10 |  |  |
| 109.3 | Saw Cutting groves saw-cuts exceeding 70mm but not exceeding 90mm in depth | m | 10 |  |  |
| 109.4 | Take up or down and remove to tip off site existing steel fence | m | 25 |  |  |
| 109.5 | Demolition of building or structure, existing deck and remove to tip off site | m³ | 15 |  |  |
| 109.6 | Demolition of building or structure, existing abutments and remove to tip off site | m³ | 15 |  |  |
| 109.7 | Demolition of building or structure, existing box culverts and remove to tip off site | m³ | 23 |  |  |
| 109.8 | Take up or down and remove to tip off site existing gabion baskets | m³ | 5 |  |  |
| 109.9 | Demolition of building or structure, existing Walls and set aside for reuse | m³ | 5 |  |  |
|  | CC 201/MMHW Pavement foundation construction |  |  |  |  |
| 201.1 | Type 1 unbound mixture sub-base in carriageway, hard shoulder and hard strip | m³ | 3 |  |  |
|  | CC 202/MMHW Flexible pavement construction |  |  |  |  |
| 202.1 | Hot Rolled Asphalt high stone content 10mm aggregate surface course 55PSV 40mm thick in carriageway, hard shoulder and hard strip 125 pen | m² | 45 |  |  |
| 202.2 | Dense Bitumen Macadam 20mm aggregate binder course 60mm thick in carriageway, in carriageway, hard shoulder and hard strip 125 pen | m² | 40 |  |  |
| 202.3 | Dense Bitumen Macadam 32mm aggregate base course 140mm thick in carriageway, hard shoulder and hard strip 125 pen strip 125 pen | m² | 38 |  |  |
|  | CC 205/MMHW Maintenance of pavements with an asphalt surfacing |  |  |  |  |
| 205.01 | Milling pavement 40mm | m² | 1.5 |  |  |
| 205.01 | Milling pavement 100mm | m² | 1.5 |  |  |
|  | CC 482/MMHW Structural concrete |  |  |  |  |
| 482.1 | Structural concrete C40/50 bridge deck | m³ | 15 |  |  |
| 482.2 | Structural concrete C40/50 Apron | m³ | 15 |  |  |
| 482.3 | Structural concrete C40/50 Behind wing walls | m³ | 9 |  |  |
| 482.4 | Structural concrete no fines concrete fill to structure | m³ | 22 |  |  |
| 482.5 | Structural concrete C20/25 Boundary wall footing | m³ | 2 |  |  |
| 482.6 | Precast concrete Box Culvert 2.4m wide 1.4m high cross section area 3.36 m² | n | 6 |  |  |
| 482.7 | Bar reinforcement nominal size 20mm in Bridge deck | kg | 1895 |  |  |
| 482.8 | Bar reinforcement nominal size 10mm in Bridge deck | Kg | 81 |  |  |
| 482.9 | Fabric reinforcement to BS A393 Bridge Deck | m² | 60 |  |  |
| 482.10 | Fabric reinforcement to BS A393 Wing Walls | m² | 12 |  |  |
| 482.11 | Fabric reinforcement to BS A393 Aprons | m² | 35 |  |  |
|  | CC 488/MMHW Waterproofing for concrete structures |  |  |  |  |
| 488.1 | Waterproofing concrete deck of highway structure with 1 coats of servidek more than 300 mm wide horizontal or at any inclination up to and including 30° to the horizontal (Deck) | m² | 55 |  |  |
| 488.2 | Waterproofing concrete deck of highway structure with 1 coats of servidek more than 300 mm wide at any inclination more than 30° up to and including 90° to the horizontal (Deck Sides ) | m² | 9 |  |  |
| 488.3 | Waterproofing concrete box culvert structure with 1 coats of servidek than 300 mm wide horizontal or at any inclination up to and including 30° to the horizontal (Culvert top) | m² | 29 |  |  |
|  | Waterproofing concrete box culvert structure with 1 coats of servidek more than 300 mm wide at any inclination more than 30° up to and including 90° to the horizontal (Culvert Sides) | m² | 5 |  |  |
|  | CC 490/MMHW Bridge expansion joints and sealing of gaps |  |  |  |  |
| 490.1 | Butyl Sealant joint | m | 38 |  |  |
|  | CC 491/MMHW Masonry |  |  |  |  |
| 491.1 | Random rubble uncoursed to match existing stonework in masonry mortar designation (ii) in walls (Boundary Wall) | m³ | 15 |  |  |
| 491.2 | Stonework coping in masonry mortar designation (ii) (Boundary Wall) | m | 12.5 |  |  |
| 491.3 | Random rubble uncoursed to match existing stonework in masonry mortar designation (ii) in walls (Wing walls) | m³ | 10 |  |  |
| 491.4 | Stonework coping in masonry mortar designation (ii) (Wing wall1) | m | 13 |  |  |
| 491.5 | Random rubble uncoursed to match existing stonework in masonry mortar designation (ii) in walls (Rebuild) | m³ | 2 |  |  |
|  | CC 500/MMHW Drainage |  |  |  |  |
| 500.1 | 150mm internal diameter HDPE Perforated drain in trench depth to invert not exceeding 2 metres, average depth to invert 1m | m | 9 |  |  |
| 500.2 | 150mm internal diameter HDPE Perforated drain in trench depth to invert not exceeding 2 metres, average depth to invert 1m culvert drainage | m | 24 |  |  |
| 500.3 | Type B (20-40mm) filter material contiguous with filter drain | m³ | 7 |  |  |
|  | CC 601/MMHW Earthworks |  |  |  |  |
| 601.1 | Excavation of acceptable material Class 5A (Existing Verge) | m³ | 8 |  |  |
| 601.2 | Excavation of unacceptable material Class U1A in structural foundations 0 to 3 meters (Culvert Foundation) | m³ | 50 |  |  |
| 601.3 | Excavation of unacceptable material Class U1A in structural foundations 0 to 3 meters (Deck) | m³ | 8 |  |  |
| 601.4 | Excavation of unacceptable material Class U1A in structural foundations 0 to 3 meters (Wing walls) | m³ | 10 |  |  |
| 601.5 | Disposal of unacceptable earthworks material Class U1A (Culvert + Wing Walls) | m³ | 68 |  |  |
| 601.6 | Disposal of unacceptable earthworks material Class U2 (Plannings) | m³ | 0.2 |  |  |
| 601.7 | Topsoiling 150mm thick to surfaces sloping at 10º or less to the horizontal | m² | 51 |  |  |
| 601.8 | Imported acceptable earthworks material 6K in lower bedding for box culvert structure in culvert foundation | m³ | 6 |  |  |
| 601.9 | Imported acceptable earthworks material 6L in upper bedding for box culvert structure in culvert foundation | m³ | 2 |  |  |
|  | LC 127/MMHW Fencing |  |  |  |  |
| 127.1 | Temporary stockproof fencing | m | 30 |  |  |
| 127.2 | Timber Post and four rail fencing 1.2m High with stockproof fencing as detailed on drawings T104 | m | 25 |  |  |

| The total of the Prices |  |
| --- | --- |

The method and rules used to compile the Price List are

The contractor shall price all items accordingly and allow for all item coverages i.e. supply and install. In accordance with manufacturers recommendations or highway work specifications identified in this document. The rates and prices entered in the Price List shall be deemed to be the full inclusive value of the work covered by the several items including the following, unless expressly stated otherwise: i. Labor and costs in connection therewith. ii. The supply of materials, goods, storage and costs in connection therewith including delivery to Site. Taking delivery of materials and goods supplied by others, unloading, storage, and costs in connection therewith. iii. Plant and costs in connection therewith. iv. Fixing, erecting and installing or placing of materials and goods in position. v. Temporary Works. vi. The effect on the phasing of the Works or any element of the Works to the extent set forth or reasonably implied in the documents on which the tender is based. vii. General obligations, liabilities and risks involved in the execution of the Works set forth or reasonably implied in the documents on which the tender is based. viii. Establishment charges, overheads and profit. ix. Waste. x. Attendance and transport for sampling and testing carried out by the Engineer, tests carried out by the Contractor, supplying results of tests carried out by the Contractor and providing test certificates. xi. Complying with Quality Assurance schemes and providing certificates of conformity. xii. Preparation and supply of detailed working drawings. xiii. Awaiting approvals and or consents.

## Scope

1 Description of the works

The Contractor is required to do the following: Preliminaries, H&S, Environmental - Set up temporary site welfare and secure site with double-clipped Herras type fencing around site compound. - All health and safety in accordance with VOL 4 Pre-construction Information - Working hours shall be agreed in advance and any noisy works shall be scheduled to minimize disruption - Install suitable Over pumping and monitoring system Traffic Management and Public Information - Provide local letter drop informing of the works with Contractor’s contact details 1 week in advance to affected properties. - Install advance warning signs informing that road is closed for the duration of the works. - Establishment, maintenance and removal of road closure and temporary diversion route Site Preparation/Clearance - General site clearance - The Contractor shall clear the work area of any obstructions, debris, or vegetation necessary to access the working area - Extents are shown on the drawings in Volume 3. - Monitor the Met office 5 day forecast in regards to potential flood events and communicate potential issues to the Client - Clearing and levelling of the designated site area. - Setting out works in accordance with approved drawings. - Excavation and disposal of surplus materials to approved locations. - Provision of temporary access and protection measures during construction. Permanent works - Excavation/demolition of existing culvert and historic abutment and remove to tip off site - Excavation to foundation level for proposed box culvert and installation of bedding materials - Installation of box culvert as show on drawing ERCF2509N T104 to include design check certificate and AIP. - Back fill with no fines concrete with perforated 150mm DIA pipe for back of culvert drainage. - Installation of wingwalls with masonry facing and C40/50 concrete as shown on drawings ERCF2509N T104 - Installation of Bridge Deck C40/C50 concrete wall with 20mm Bars bottom and 1 layers of A393 mesh top, B10 bars links to support A393 mesh as shown on drawings ERCF2509N T104 - Reinstate carriageway to pavement construction P1 - Installation of new boundary wall - Installation of post and rail fencing - Installation of highway drainage area with 40mm stone Reinstatement of fields - Allow for landscaping and reinstatement of disturbed areas as a consequence of undertaking the Works Quality & Compliance - Materials and workmanship to conform to relevant BS/EN standards. - Inspections and approvals by the supervising engineer prior to handover. Completion - Disposal of all arising’s to licenced tip. - The Works will be deemed complete when all the works are complete the road is open, temporary welfare/site compound are removed and the surrounding area made good. - Provide a Health & Safety File

2 Drawings

| DRAWING NUMBER | REVISION | TITLE |
| --- | --- | --- |
| ERCF2509N 20 T101 | A | Site Location Plan & Site Extents |
| ERCF2509N 20 T102 | A | Existing General Arrangement |
| ERCF2509N 20 T103 | A | Existing Culvert Arrangement |
| ERCF2509N 20 T104 | A | Proposed General Arrangement |
| ERCF2509N 20 T105 | A | Proposed Culvert Arrangement |
| ERCF2509N 20 T201 | A | Site Clearance |
| ERCF2509N 20 T601 | A | Earthworks |

Scope

3 Specifications

| TITLE | DATE OR REVISION | TICK IF PUBLICLY AVAILABLE |
| --- | --- | --- |
| Manual of Contract Documents for Highway Works. Volume 1 – Specification for Highway Works | March 1999 with revisions May 2018 | ✓ |

4 Constraints on how the Contractor Provides the Works

The Met Office 5 Day forecast should be monitored by the Contractor. Road closure has been applied for by overseeing organization. OWC has been applied for

Scope

5 Requirements for the programme

A Gantt bar chart programme is required showing the principal activities and their sequence, including the critical path and float.

6 Services and other things provided by the Client

| ITEM | DATE BY WHICH IT WILL BE PROVIDED |
| --- | --- |
| Agreement for access to the adjacent fields to undertake works | From 07/09/2026 |
| Road closure | From 07/09/2026 |
| OWC | From 07/09/2026 |

## Site Information

The existing culvert has suffered erosion, and water is now bypassing the culvert causing the carriageway to begin to sag. Statutory Undertakers equipment searches indicate the following. See stats returns in Appendix B. In Summary - There is Openreach overhead apparatus to the north of the site - There is DCWW None - There is WWU LP None - There is SP Energy None Contractor to CAT scan for services prior to any excavations.

### Freedom of Information Act 2000 Declaration

Conwy County Borough Council

Environment, Roads and Facilities

Pont Gell, Llangernyw

The Freedom of Information Act 2000 applies to all the activities of Conwy County Borough Council (CCBC).

As a supplier of goods and services to CCBC, you should be aware of CCBC’s obligations and responsibilities under the Freedom of Information Act 2000 to provide on request access to recorded information held by it.  One of the consequences of those new statutory responsibilities is that information CCBC holds about your organisation may be subject to disclosure in response to a request, unless CCBC decides that one of the various statutory exemptions applies.

Where you provide any information to CCBC that you regard as confidential and / or commercially sensitive then you must make it clear in your documentation as to the information to which you consider a duty of confidentiality applies.  The use of blanket protective markings such as “commercial in confidence” will no longer be appropriate and a clear indication as to what material is to be considered confidential and reason why should be given.

CCBC cannot accept that trivial information or information which by its very nature cannot be regarded as confidential should be subject to any obligation of confidence.

In certain circumstances where information has not been provided in confidence, CCBC may still wish to consult with you as to the application of any other exemption such as that relating to disclosure that will prejudice the commercial interests of any party.  However the decision as to what information will be disclosed will be reserved to CCBC.

NOTE: Detailed cost information within the pricing document is considered to be of commercial interest and will not be disclosed.

If you require any advice on what the Freedom of Information Act 2000 involves, please contact the Information Governance Unit on 01492 577215, E-mail info-gov.unit@conwy.gov.uk.

List below any items you consider confidential or commercially sensitive:

Signed by:…………………………………………………………………………………………………………………………….…..

For and on behalf of:

Name…………………………………………………………………………………………………………………………………...…

Address……………………………………………………………………………………………………………………………….….

…………………………………………………………………………………………………………………………………………….

Date:………………………………………………………

### Anti-Collusion Certificate

Conwy County Borough Council

Environment, Roads and Facilities

Pont Gell, Llangernyw

I/We certify that this tender is made in good faith, and that we have not fixed or adjusted the amount of the tender by or under or in accordance with any agreement with any other person.  I/We also certify that we have not and I/We undertake that we will not before the award of any contract for the work:

(i) disclose the tender price or any other figures or other information in connection with the tender to any other party (including any other company or part of a company forming part of a group of companies of which I am/We are a part) nor to any sub-contractor (whether nominated or domestic or howsoever appointed) nor supplier (whether nominated or domestic or howsoever appointed) or any other person to whom such disclosure could have the effect of preventing, restricting or distorting competition in this tendering exercise;

(ii) enter into any agreement or arrangement with any person that they shall refrain from tendering, that they shall withdraw any tender once offered or vary the amount of any tender to be submitted;

(iii) Otherwise collude with any person with the intent of preventing, restricting or distorting competition;

(iv) pay, give or offer to pay or give any sum of money or other valuable consideration directly or indirectly to any person for doing or having done or causing or having caused to be done in relation to any other tender or proposed tender for the work any act or thing of the sort described at (i), (ii) or (iii) above.

I/We further declare that I/We have no knowledge either of the sum quoted or of any other particulars of any other tender for this work by any other party.

I/We further certify that the principles described above have been, or will be, brought to the attention of all sub-contractors, suppliers and associated companies providing services or materials connected with the tender and any contract entered into with such sub-contractors, suppliers or associated companies will be made on the basis of compliance with the above principles by all parties.

I/We acknowledge that any breach of the foregoing provisions shall lead automatically to this tender being disqualified and may lead to criminal or civil action.

Conwy County Borough Council shall treat any tender received in confidence but reserves the right to make same available to any relevant Department of the Council, other Local Authority Trading Standards Department, the Director General of Fair Trading, and/or any other statutory regulatory authority either having jurisdiction over the work or who may now or at any time in the future have statutory power to require disclosure of this tender.

In this certificate, the word ‘person’ includes a body of persons corporate or unincorporated and any undertaking for the purposes of The Competition Act 1998; any agreement includes any transactions, formal or informal and whether legally binding or not; and the ‘work’ means the work or goods or services in relation to which this tender is made.

Signature…………………………..……….    in the capacity of……………………….……..….. (e.g. Director, Secretary etc)

Date……………….…………………….….

Duly authorised to sign tenders and acknowledge the contents of the anti-collusion certificate for and on behalf of:-

……………………………….………………………….…………………….……………………........................... (Name of firm)

Full postal address ………………………………………………………………………………………………..………….…..........

………………………………………………………………………………...…...........….Post Code………………………………..

Signed by  :………………… . . . . . . . . . . . . . . .. . . For and on behalf of :………………………………………………… . . . .

### Declaration

Conwy County Borough Council

Environment, Roads and Facilities

Pont Gell, Llangernyw

In this certificate, any reference to person or persons shall mean and include businesses, associations or corporations and any reference to arrangements or agreements shall mean any and all transactions, formal or informal, lawful or otherwise.

I / We certify that:

- We have not been convicted of nor are currently under investigation for any acts of conspiracy, corruption, bribery, fraud, money laundering, such acts as defined by the relevant UK law.

- We are not bankrupt nor have had a receiving order or administration order or bankruptcy restrictions order made against us nor are in the process of or about to commence any composition or arrangement with or for the benefit of our creditors or, if registered as a partnership under Scots law have not been granted a trust deed or is subject of a petition for sequestration of our estate.

- We have not, nor are about to, be subject of a resolution or order for winding up, nor have has a receiver, manager or administrator.

- We have not been convicted of a criminal offence relating to the conduct of our business or (being an individual) not been guilty of grave misconduct in the course of its business.

- We have fulfilled our obligations relating to the payment of social security contributions and the payment of taxes in accordance with the legal provisions of the country in which it is established and/or the United Kingdom.

- We have not been found guilty of serious misrepresentation in providing any information under Section 57 to 60 of the Procurement Act 2023 (as amended) within the last three (3) years.

- We have not suffered a deduction for liquidated or ascertained damages in respect of any contract nor had a contract cancelled, or not renewed, for failure to perform nor been the subject of a claim (contractual or otherwise) based upon a failure of quality in design, work, materials or services within the last three years.

- None of the senior personnel of the organisation have been involved (in a similar position) in any company which has gone into insolvent liquidation, voluntary arrangement, receivership or administration or been declared bankrupt.

- We comply with the requirements of the Equalities Act 2010.

I / We confirm and attest that the foregoing information and declarations are accurate to the best of my / our knowledge and that I / We acknowledge and accept that any false information could result in our application being rejected, or, in the event that any false declaration is discovered after the award of any contract, may lead to the rescission of any contract awarded.

Dated……………………………………………..……..

Signature………………………………………..………………………………………………………………………………………..

Name (printed)…………………………….……………………………………………………………………………………………..

Capacity / Title……………………………………………………………………………………………………………………………

For and on behalf of …………………………………………………………………………………………………………………..…

# Appendix 1 - Quality Questionnaire

Guidance Notes

Please read these guidance notes carefully before completing this document.

All parts of the Quality Questionnaire must be answered.

- The questionnaire is to be completed by suitably qualified and experienced Companies who wish to tender for the Contract titled Pont Gell, Llangernyw

- Companies shall refer to Volume 1 - Instructions to Tenderers, which sets out the procedure which Conwy County Borough Council shall follow in procuring this Contract.

- Where an applicant is required to submit relevant supporting information, it should be provided within a separate appendix and cross-referenced to correspond with the relevant section of the questionnaire.

- Tenderers shall note that answers to questions and submitted information must be both relevant and concise. The Evaluation Team appraising these tenders shall deduct marks where answers are found to be generic in nature or contain little relevance to the work in question. The Company shall ensure that their submission is both well formatted and easily navigable by the Evaluation Team.

- Tenders returned with any sections or questions left unanswered are liable to be rejected without further consideration.

- No more than 1000 words are required per answer

| Q1 | The Contractors proposed approach and methodology for the delivery of the proposed work. |
| --- | --- |

| Q2 | The Contractor’s proposed approach to Project Management during execution of the works including key staff, duties and management and co-ordination of sub-contractors. |
| --- | --- |

| Q3 | The Contractor’s proposed approach to managing Health and Safety for the works and protecting the environment. |
| --- | --- |

| Q4 | The Contractor’s proposed approach to progress reporting and communication with Conwy County Borough Council during execution of the works, including the approach to reporting commercial issues. |
| --- | --- |

| Q5 | The Contractor’s approach to managing the quality of output on site, checking and supervision of the works. |
| --- | --- |

| Q6 | The Contractor’s perceived key risks in undertaking the works and the outline mitigation measures. |
| --- | --- |

| Q7 | - The Contractor’s outline programme for the works including details of: - Start date, access dates, key dates and completion date. - Order and sequencing of the works. - Provisions for risk allowance. Details of each planned operation including any resourcing and sub-contractor requirements. |
| --- | --- |