## Lists (hidden)
To create a drop-down list from a range of cells, select the range of cells and then assign a name in the box to the bottom left of the ribbon. To edit or delete a named range CTRL+F3 |  | The company name lists (eg Archlist) change depending on the SCP name selected on the Project details sheet. A change of name in a green-shaded cell will automatically update the drop-down list on the Project details sheet
Partnerrole | LHB/Trust | SCPs |  | Balfour Beatty | BAM | Interserve | Assessors
LHB/T | Abertawe Bro Morgannwg | [5 empty] | LHB/T
PM | Aneurin Bevan | PMs |  | G&T | Gleeds | Mace | PM
CA | Betsi Cadwaladr | [5 empty] | CA
CDMC | Cardiff & Vale | CAs |  | G&T | Gleeds | Sweett | CDMC
Super | Cwm Taf | [5 empty] | Super
Arch | Hywel Dda | ARCHlist |  | Balfour Beatty | BAM | Interserve | SCP
CSE | Powys | #REF! |  | Atkins | Stantec | Boyes Rees
BSE | PH Wales | #REF! |  | Keppie | CODA | HLMAD
SCP | Velindre
WAS
Buildingtype |  | CSElist |  | Balfour Beatty | BAM | Interserve
Mental Health |  | #REF! |  | Atkins | Ove Arup | Opus
LGH | Projectstage | #REF! |  | Buro Happold | Ramboll | WSP
SCCC | SOC
CH | OBC
Specialist Unit | FBC | BSElist |  | Balfour Beatty | BAM | Interserve
Other | Design Completion and Construction | #REF! |  | Atkins | Hulley and Kirkwood | Hoare Lea
| Operational commissioning | #REF! |  | Buro Happold | Ove Arup | WSP
Projecttype | Project closure
New build
Refurburbishment |  | CDMlist |  | Balfour Beatty | BAM | Interserve
Mixed | Scale | #REF! |  | F+G | Harris & Porter | Richard Parfitt
| 10 | #REF! |  | Buro Happold | Ove Arup | WSP
9
BREEAM Rating | 8 | BSIlist |  | Balfour Beatty | BAM | Interserve
Outstanding | 7 | #REF! |  | Shepherd Engineering | Balfour Beatty | Interserve
Excellent | 6 | #REF! |  | T Clarke | Lorne Stewart | SPIE Matthew Hall
Very good | 5
Good | 4 | SVlist |  | Balfour Beatty | BAM | Interserve
Pass | 3 | #REF! |  | SV BB1 | SV BAM1 | SV Int1
Unclassified | 2 | #REF! |  | SV BB2 | SV BAM2 | SV Int2
- | 1
-
Assessors scorecards to be completed
Region | Energyrating |  | LHB/T | PM, CA, CDMC, Super, Arch, SCP
N Wales | A |  | PM | LHB-Trust, CA, CDMC, Super, Arch, CSE, BSE, BSI, SCP
SE Wales | B |  | CA | LHB-Trust, PM, SCP
SW Wales | C |  | CDMC | SCP
| D |  | Super | SCP
| E |  | SCP | LHB-Trust, PM, CA, CDMC, Super, Arch, CSE, BSE, BSI
Wastetarget
BREEAM project type classification | Construction
New build | Refurb/strip out
Refurb | Demolition
Excavation
Data entry
No KPI data to report

## 6-monthly Project data (hidden)
6-monthly KPI Report: Complete the Safety, Local Labour and Local Suppliers KPIs, the Company Performance KPIs and the Client Performance KPIs
#REF! |  |  |  | #REF! | #REF! | #REF!
KPI |  |  | Data | Performance | Star rating | Comments
Safety | F | Safety | Data | Performance | Star rating | Comments
| 1 | Total number RIDDOR accidents on project to date | 7 |  |  |  | Automatically updates from End of project performance sheet
| 2 | Total hours worked on project to date (own labour) | 587256 |  |  |  | 50% | 30% | 25% | 0% | 0 | This row used in star formula
| 3 | Total hours worked on project to date (subcontractors) | 158742 |  |  |  | AFR>0.50 | AFR = 0.50- 0.30 | AFR = 0.30 - 0.25 | AFR = 0.25-0.01 | AFR = 0 (Zero reportable accidents)
| 4 | AFR for project to date |  | 0.93834 | *
| 5 | Approx AIR for project to date |  | 1876.6806
Sustainability
| J | Local labour - distance travelled to work | No of employees | Performance | Star rating | Comments
| 1 | 0-20 miles (within Wales) | 125 | 52.3%
| 2 | 21-50 miles (within Wales) | 78 | 410.5%
| 3 | 50+ miles (within Wales) | 12 | 63.16%
| 4 | Outside Wales | 24 | 10.04%
| 5 | Total employees | 239 |  |  |  | 0.5 | 0.6 | 0.7 | 0.8 | 0.8 | This row used in star formula
| 6 | % within Wales |  | 89.96% | ***** |  | <50% | 50% - 60% | 60% - 70% | 70% - 80% | >80%
| K | Local suppliers and subcontractors | £ | Performance | Star rating | Comments
| 1 | Construction value | 1750000
| 2 | Total value of supplier and subcontract packages let to date | 1652000
| 3 | Welsh-let value to date | 1500000
| 4 | % of construction value let to date |  | 94.4% |  |  | 0.5 | 0.6 | 0.7 | 0.8 | 0.8 | This row used in star formula
| 5 | % within Wales |  | 90.8% | ***** |  | <50% | 50% - 60% | 60% - 70% | 70% - 80% | >80%

## Intro
KPI Measurement and Reporting:
1 | Complete the Project Details data fields at the top of all scoresheets issued for completion.
2 | Every project report the following KPI data for all live projects:
3 | Self-assessment and collaborative scoring is not permitted.
4 | Use the following 10 point scale to complete the Framework performance KPIs:
10 Totally satisfied / Exceptional performance
9 Very satisfied / Excellent performance
8 Satisfied / Very good performance
7 Mostly satisfied - Good performance
6 Neutral - tending towards satisfied
5 Neutral - tending towards dissatisfied
4 Somewhat dissatisfied / several areas less than satisfactory
3 Mostly dissatisfied - many areas less than satisfactory
2 Very dissatisfied / Unacceptable performance in several areas
1 Totally dissatisfied / Unacceptable performance in almost all areas
- Not Applicable
Guidance on the 1-10 scale used for assessing the impact of defects is available by hovering the mouse over the defects data collection section of End of Project data form.
5 | Completed forms wil be scrutinised and reviewed at an annual review meeting to be arranaged post contract completion

## PM
Survey of Project Manager Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor | [6 empty] | new build | refurbishment | mixed
Score using the 1-10 scale. |  |  | Comments | Score | Comments | Score | Comments | Score |  | Score
A: | Quality of core services
1 | The Project Manager manages the team efficiently to produce a fully integrated design. |  |  | - |  | - |  | -
2 | The Project Manager understands the contract and carries out their duties as Contractor under it. |  |  | - |  | - |  | -
3 | The Project Manager ensures that risk management systems are in place and risk is managed proactively, regularly and effectively. |  |  | - |  | - |  | -
4 | The Project Manager ensures that change management systems are in place, ensuring that change is identified early on and managed proactively and effectively. |  |  | - |  | - |  | -
5 | The Project Manager leads and manages the contractor well. |  |  | - |  | - |  | -
6 | The Project Manager produces documents to a high standard and holds the construction and design team to the same standards. |  |  | - |  | - |  | -
B: | Timely delivery of services/information
1 | The Project Manager efficiently manages time of the design team members. |  |  | - |  | - |  | -
3 | The Project Manager delivers their documents and information to programme. |  |  | - |  | - |  | -
C: | Commitment to key project objectives
1 | The Project Manager manages the programme proactively and has put systems and procedures into place to mitigate delay and ensure change request impact is managed. |  |  | - |  | - |  | -
2 | The Project Manager ensures that appropriate cost control systems and reporting mechanisms are in place. |  |  | - |  | - |  | -
3 | The Project Manager ensures that appropriate quality management systems and reporting mechanisms are in place for design activities. |  |  | - |  | - |  | -
4 | The Project Manager ensures that sustainability issues are a key consideration of the design process and are followed through during construction with clear monitoring systems in place. |  |  | - |  | - |  | -
D: | Collaborative approach
1 | The Project Manager has established clearly defined objectives for the constructors and design team. |  |  | - |  | - |  | -
2 | The Project Manager has ensured all team members understand their roles and responsibilities and those of others. |  |  | - |  | - |  | -
3 | The Project Managr has set down appropriate communication processes which are open and honest and facilitate information sharing. |  |  | - |  | - |  | -
4 | The Project Manager actively identifies and facilitates necessary for design and team training. |  |  | - |  | - |  | -
E: | Appropriate resourcing
1 | The Project Manager spend adequate time on the project to discharge their duties. |  |  | - |  | - |  | -
2 | All member of the Project Managers Team have an adequate level of ability and experience to manage the project and project effectively. |  |  | - |  | - |  | -
F: | Commitment to safety
1 | All members of the project management team demonstrates a competent awareness of health and safety legislation and ensures the CDM regulations are adhered to. |  |  | - |  | - |  | -
2 | All members of the project management team promotes vigilant health and safety awareness within the design team. |  |  | - |  | - |  | -
3 | All members of project management team promotes vigilant health and safety awareness within the construction team with clear evidence of site procedures in place to manage health & safety. |  |  | - |  | - |  | -
Performance summary |  |  | Comments | Score | Comments | Score | Comments | Score |  | Score
A: | Quality of core services |  |  | - |  | - |  | - |  | -
B: | Timely delivery of services/information |  |  | - |  | - |  | - |  | -
C: | Commitment to key project objectives |  |  | - |  | - |  | - |  | -
D: | Collaborative approach |  |  | - |  | - |  | - |  | -
E: | Appropriate resourcing |  |  | - |  | - |  | - |  | -
F: | Commitment to safety |  |  | - |  | - |  | - |  | -
G: | Overall Performance |  |  | - |  | - |  | - |  | -
OVERALL RATING : |  |  | Comments: |  | Comments: |  | Comments:
Note on A3: The framework partner who is providing the feedback on performance

## BSE
Survey of Building Services Engineer Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor |  |  | new build | refurbishment | mixed
Score using the 1-10 scale. |  |  | Comments | Score |  | Score
A: | Quality of core services
1 | The BSE manages their team efficiently to produce a fully integrated design.
2 | The BSE knows the contract and carries out their duties as Contractor under it.
3 | The BSE ensures that risk management systems are in place and risk is managed proactively, regularly and effectively.
4 | The BSEensures that change management systems are in place, ensuring that change is identified early on and managed proactively and effectively.
5 | The BSE leads the contractor well.
6 | The BSE produces documents to a high standard and in a timely manner
7 | The BSE manages their requirments under the programme proactively and has put systems and procedures into place to mitigate delay and ensure change request impact is managed.
8 | The BSE ensures that sustainability issues are a key consideration of the design process and are followed through during construction with clear monitoring systems in place.
9 | The BSE has appropriate communication processes which are open and honest and facilitate information sharing.
10 | The BSE spend adequate time on the project to discharge their duties.
11 | All member of the BSE have an adequate level of ability and experience to manage the project and project effectively.
12 | All members of the BSE demonstrates a competent awareness of health and safety legislation and ensures the CDM regulations are adhered to.
13 | All members of the BSE promotes vigilant health and safety awareness within the design and construction team.
Performance summary |  |  | Comments | Score |  | Score
0
OVERALL COMMENTS
Note on A3: The framework partner who is providing the feedback on performance

## AST
Survey of Architectural Services Team Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor |  |  | new build | refurbishment | mixed
Score using the 1-10 scale. |  |  | Comments | Score |  | Score
A: | Quality of core services
1 | The AST manages their team efficiently to produce a fully integrated design.
2 | The AST knows the contract and carries out their duties as Contractor under it.
3 | The AST ensures that risk management systems are in place and risk is managed proactively, regularly and effectively.
4 | The ASTensures that change management systems are in place, ensuring that change is identified early on and managed proactively and effectively.
5 | The AST leads the contractor well.
6 | The AST produces documents to a high standard and in a timely manner
7 | The AST manages their requirments under the programme proactively and has put systems and procedures into place to mitigate delay and ensure change request impact is managed.
8 | The AST ensures that sustainability issues are a key consideration of the design process and are followed through during construction with clear monitoring systems in place.
9 | The AST has appropriate communication processes which are open and honest and facilitate information sharing.
10 | The AST spend adequate time on the project to discharge their duties.
11 | All member of the AST have an adequate level of ability and experience to manage the project and project effectively.
12 | All members of the AST demonstrates a competent awareness of health and safety legislation and ensures the CDM regulations are adhered to.
13 | All members of the AST promotes vigilant health and safety awareness within the design and construction team.
Performance summary |  |  | Comments | Score |  | Score
0
OVERALL COMMENTS
Note on A3: The framework partner who is providing the feedback on performance

## S&C
Survey of Structural & Civil Team Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor |  |  | new build | refurbishment | mixed
Score using the 1-10 scale. |  |  | Comments | Score |  | Score
A: | Quality of core services
1 | The S&C manages their team efficiently to produce a fully integrated design.
2 | The S&C knows the contract and carries out their duties as Contractor under it.
3 | The S&C ensures that risk management systems are in place and risk is managed proactively, regularly and effectively.
4 | The S&Censures that change management systems are in place, ensuring that change is identified early on and managed proactively and effectively.
5 | The S&C leads the contractor well.
6 | The S&C produces documents to a high standard and in a timely manner
7 | The S&C manages their requirments under the programme proactively and has put systems and procedures into place to mitigate delay and ensure change request impact is managed.
8 | The S&C ensures that sustainability issues are a key consideration of the design process and are followed through during construction with clear monitoring systems in place.
9 | The S&C has appropriate communication processes which are open and honest and facilitate information sharing.
10 | The S&C spend adequate time on the project to discharge their duties.
11 | All member of the S&C have an adequate level of ability and experience to manage the project and project effectively.
12 | All members of the S&C demonstrates a competent awareness of health and safety legislation and ensures the CDM regulations are adhered to.
13 | All members of the S&C promotes vigilant health and safety awareness within the design and construction team.
Performance summary |  |  | Comments | Score |  | Score
0
OVERALL COMMENTS
Note on A3: The framework partner who is providing the feedback on performance

## CA
Survey of Cost Advisor / Contract Admin Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor
Score using the 1-10 scale. |  |  | Comments | Score | Comments | Score
A: | Quality of service
1 | The CA supports the PM in the running of the contract. |  |  |  |  | -
2 | The CA ensures that risks are accurately quantified from a financial perspective. |  |  |  |  | -
3 | The CA ensures that the financial aspect of change management is controlled and managed efficiently. |  |  |  |  | -
4 | The CA produces accurate and relevant cost plans. |  |  |  |  | -
5 | The CA actively manages the costs on the project and produces reliable and accurate cost reports and cash flow forecasts, to ensure that the budget is maintained. |  |  |  |  | -
6 | The CA produces documents to a high standard. |  |  |  |  | -
7 | The CA drives the concept of "best value for money" through utilisation of VM and VE techniques. |  |  |  |  | -
8 | The CA carries out valuations effectively and accurately values the works. |  |  |  |  | -
9 | The CA facilitates the timely and accurate agreement of the final account. |  |  |  |  | -
10 | The CA manages procurement and tendering processes effectively. |  |  |  |  | -
11 | The CA delivers their documents and information to programme. |  |  |  |  | -
12 | The CA appreciates the importance of maintaining the project programme and contributes to efforts to keep the project on track. |  |  |  |  | -
13 | The CA ensures that appropriate cost control systems and reporting is carried out on a regular basis. |  |  |  |  | -
14 | The CA understands their roles and responsibilities and those of others. |  |  |  |  | -
15 | The CA shares information freely and communicates openly and honestly. |  |  |  |  | -
16 | The CA actively contributes to collaborative and cooperative working throughout the team. |  |  |  |  | -
17 | The CA has adequate time to spend on the project and invests the necessary time to discharge their duties. |  |  |  |  | -
18 | The CA has an adequate level of ability and experience to manage the project costs effectively. |  |  |  |  | -
Performance summary |  |  | Comments |  | Comments | Score
| Overall Performance |  |  | 0 |  | -
CA star rating: |  |  | Comments: |  | Comments:
Note on A3: The framework partner who is providing the feedback on performance

## CDM PD
Survey of PD/CDM Performance
Assessor details |  | Project details:
Company |  | Project
Date |  | Assessor
Score using the 1-10 scale. |  |  | Comments | Score | Comments | Score | Score
A: | Quality of core services
1 | The Advisor ensures that the client and project team are fully aware of their duties under the CDM regulations. |  |  | - |  | -
2 | The CDM Advisor produces an accurate and bespoke set of Pre-construction Information. |  |  | - |  | -
3 | The CDM Advisor ensures that the F10 notice is issued in a timely manner and kept up to date. |  |  | - |  | -
4 | The CDM Advisor carries out a thorough review of the construction phase health and safety plan. |  |  | - |  | -
5 | The CDM Advisor advises the Client on the competency of the project team in connection with the CDM regulations. |  |  | - |  | -
6 | The CDM Advisor ensures that health & safety is accounted for in the design of the project. |  |  | - |  | -
7 | The CDM Advisor carries out regular site inspections and produces accurate reports during the construction period. |  |  | - |  | -
8 | The CDM Advisor thoroughly reviews the O&M manuals and produces an accurate and structured Health & Safety File. |  |  | - |  | -
9 | The CDM Advisor produces documents to a high standard. |  |  | - |  | -
10 | The CDM Advisor delivers their documents and information to programme. |  |  | - |  | -
11 | The CDM Advisor appreciates the importance of maintaining the project programme and contributes to efforts to keep the project on track. |  |  | - |  | -
12 | The CDM Advisor understands their roles and responsibilities and those of others. |  |  | - |  | -
13 | The CDM Advisor shares information freely and communicates openly and honestly. |  |  | - |  | -
14 | The CDM Advisor actively contributes to collaborative and cooperative working throughout the team. |  |  | - |  | -
15 | The CDM Advisor has adequate time to spend on the project and invests the necessary time to discharge their duties. |  |  | - |  | -
16 | The CDM Advisor has an adequate level of ability and experience to manage the health & safety aspects of the project effectively. |  |  | - |  | -
17 | The CDM Advisor demonstrates a high level of awareness of health and safety legislation and ensures the CDM regulations are adhered to. |  |  | - |  | -
18 | The CDM Advisor champions health and safety awareness within the project team, through both design and construction activities. |  |  | - |  | -
Performance summary |  |  | Comments | Score | Comments | Score | Score
G: | Overall Performance |  |  | - |  | - | 0
CDM Advisor star rating:
Note on A3: The framework partner who is providing the feedback on performance

## 6 monthly perf (hidden)
Project Performance Summary: 6-Monthly report
#REF!
#REF! | #REF! | #REF! |  |  |  | Overall av of all scores |  | #REF!
Company Performance overall |  | #REF! |  |  |  | #REF! | No of stars | Overall av | PM av | CA av | CDMC av | Arch av | SV av | BSE av | CSE av | SCP av | BSI av
Company performance | Quality of core services | #REF! | - | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Timely delivery of services/information | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to key project objectives | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Collaborative approach | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Appropriate resourcing | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to safety | #REF! |  | #REF! | Overall average |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
Client Performance overall |  | #REF! |  | Overall average | #REF! |  | No of stars | Av score | Individual scores
Client performance | Quality of service delivery | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | Av <6 | Av = 6-7 | Av = 7=8 | Av = 8-9 | Av = 9-10
| Timely delivery of information and decisions | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Clear aims and objectives | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Collaborative approach | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to project / appropriate resourcing of delivery team | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to safety | #REF! |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
Project performance overall |  | *** |  | Weighting | Factor | Star 'points' | Weighted star points | Rounded star rating |  | Count responses
Safety | Safety | * |  | 10% | 44.94% | 1 | 0.44944 |  |  | 3
Sustainability | Use of local labour | ***** |  | 5.25% | 23.6% | 5 | 1.1798
| Use of local suppliers/subcontractors | ***** |  | 7% | 31.46% | 5 | 1.573
|  |  |  | 22.25% | 100% |  | 3.2022 | 3
The above calculations work out the Project performance overall star rating
The weightings are dericved from the D4L table of weightings

## End of Project data (hidden)
Project completion KPI Report On completion of the project, report all Project KPIs, the Company Performance KPIs and the Client Performance KPIs
#REF! |  |  |  | #REF! | #REF! | #REF!
KPI |  |  | Data | Performance | Star rating | Comments
Cost | A | Cost v Allowance | £ | Performance | Star rating | Comments
| 1 | Target Price Comparator (£) | 10000000 | 101% | ** |  | 1.05 | 1 | 0.95 | 0.94 | 0.94 | This row used in star formula
| 2 | Final Price for Work Done to Date (£) | 10100000 |  |  |  | >105% | 105%-100% | 100%- 95% | 95%-94% | <94%
| B | Cost Predictability | £ | Performance | Star rating | Comments
| 1 | Final total of the Prices (£) | 9500000 | 98.95% | ***** |  | 1 |  |  |  | 1 | This row used in star formula
| 2 | Final assessment of Price for Work Done to Date (£) | 9400000 |  |  |  | Exceeds Target Price |  |  |  | Less than or equal to Target Price
Time | C | Time Predictability | Weeks | Performance | Star rating | Comments
| 1 | Contract programme (weeks) | 52 | 0 | ****
| 2 | Agreed changes to completion date (weeks) | 2
| 3 | Actual project duration (weeks) | 54 |  |  |  | 8 | 4 | 0 | 0 | 0 | This row used in star formula
| 4 | Weeks early or late (inc extensions) |  |  |  |  | More than 8 weeks late | 4 to 8 weeks late | 4 weeks late to 0 weeks late | On-time | Early
Quality | D | AEDET | Score out of 6 | Performance | Star rating | Comments
| 1 | Character and Innovation | 6
| 2 | Form and Materials | 5
| 3 | Staff and patient environment | 4
| 4 | Urban and social integration | 3
| 5 | Performance | 2
| 6 | Engineering | 1
| 7 | Construction | 6
| 8 | Use | 6
| 9 | Access | 6
| 10 | Space | 6 |  |  |  | 3 | 4 | 4.5 | 5 | 5 | This row used in star formula
| 11 | Overall Performance |  | 5.2 | ***** |  | Av = less than 3 | Av = 3 to 4 | Av = 4.0 to 4.5 | 4.5 to 5.0 | Av = more than 5.0
| E | Defects | Score (1-10) | Performance | Star rating | Comments | 7 | 7 | 8 | 9 | 10
| 1 | Overall condition of the completed facility with respect to defects at handover | 9 | 9 | **** |  | <7 | 7 | 8 | 9 | 10
| 2 | Number of defects appended to completion certificate | 125 | 125 | * |  | >100 | 51-100 | 26-50 | 1-25 | 0 | 100 | 50 | 25 | 0 | 0 | This row used in star formula
Safety | F | Safety | Data | Performance | Star rating | Comments
| 1 | Total number RIDDOR accidents on project to date | 1
| 2 | Total hours worked on project to date (own labour) | 152896 |  |  |  | 0.5 | 0.3 | 0.25 | 0 | 0 | This row used in star formula
| 3 | Total hours worked on project to date (subcontractors) | 365014 |  |  |  | AFR>0.50 | AFR = 0.50- 0.30 | AFR = 0.30 - 0.25 | AFR = 0.25-0.0 | AFR = 0 (Zero reportable accidents)
| 4 | AFR for project to date |  | 0.19308 | ****
| 5 | Approx AIR for project to date |  | 386.1675
Sustainability | G | BREEAM Healthcare (as built) | Score (%) | Performance | Star rating | Comments
| 1 | Management | 75%
| 2 | Health & Wellbeing | 80%
| 3 | Energy | 82%
| 4 | Transport | 41%
| 5 | Water | 93%
| 6 | Materials | 100%
| 7 | Waste | 12%
| 8 | Land Use & Ecology | 89%
| 9 | Pollution | 90% |  |  |  | <Excellent |  |  | Excellent | Outstanding | These NOT used in star rating formula!
| 10 | Total BREEAM Score | 47% |  |  |  |  | *****
| 11 | BREEAM level achieved | Excellent | 4
| 12 | Did BREEAM assess the project as New Build or Refurbishment? | Refurb | 5 | ***** |  | < Very good |  |  | Very good | Excellent | These NOT used in star rating formula!
| H | ENERGY | Rating | Performance | Star rating | Comments
| 1 | EPC rating (CO2) | C | C | *** |  | E | D | C | B | A | This row used in star formula
| I | Waste | Data | Performance | Star rating | Comments
| a | Waste: re-used and recycled material content
| 1 | Total value of materials used on the project | 25000000
| 2 | Value of reused and recycled material used in construction (£) | 8560000 |  |  |  | 0.15 | 0.175 | 0.2 | 0.225 | 0.225 | This row used in star formula
| 3 | % reused and recycled materials incorporated into project (by value) |  | 34.24% | ***** |  | <15% | 15% - 17.5% | 17.5%-20% | 20%-22.5% | >22.5%
| b | Waste generation |  |  | Star rating
| 4 | Total construction and demolition waste generated (tonnes) | 15896 | 27.9382
| 5 | Total construction and demolition waste landfilled (tonnes) | 497 | 3.127%
| 6 | Total waste generated during construction (tonnes) | 6358
| 7 | Gross internal floor area (m2) | 56897 |  |  |  | 20 | 13 | 10 | 7 | 7 | This row used in star formula
| 9 | Performance (waste generated during construction (tonnes / 100 m2 gross internal floor area) |  | 11.1746 | *** |  | >20 | 13-20 | 10-13 | 7-10 | <7
| c | Waste recovery | Tonnes | % | Star rating
| 10 | EXCAVATION waste generated | 100 |  |  |  | 0.9 | 0.95 | 0.98 | 0.99 | 0.99 | This row used in star formula
| 11 | EXCAVATION waste recovered, reused, re-cycled | 95 | 95% | *** |  | <90% | 90%-95% | 95%-98% | 98%-99% | >99%
| 12 | DEMOLITION waste generated | 56 |  |  |  | 0.8 | 0.85 | 0.9 | 0.95 | 0.95 | This row used in star formula
| 13 | DEMOLITION waste recovered, reused, re-cycled | 56 | 100% | ***** |  | <80% | 80%-85% | 85%-90% | 90%-95% | >95%
| 14 | CONSTRUCTION waste generated | 12589 |  |  |  | 0.7 | 0.8 | 0.9 | 0.95 | 0.95 | This row used in star formula
| 15 | CONSTRUCTION waste recovered, reused, re-cycled | 10258 | 81.48% | *** |  | <70% | 70%-80% | 80%-90% | 90%-95% | >95%
| 16 | REFURB/STRIP OUT waste generated | 25 |  |  |  | 0.6 | 0.7 | 0.8 | 0.9 | 0.9 | This row used in star formula
| 17 | REFURB/STRIP OUT waste recovered, reused, re-cycled | 0 | 0% | * |  | <60% | 60%-70% | 70%-80% | 80%-90% | >90%
| J | Local labour - distance travelled to work | No of employees | Performance | Star rating | Comments
| 1 | 0-20 miles (within Wales) | 100 | 55.56%
| 2 | 21-50 miles (within Wales) | 50 | 27.78%
| 3 | 50+ miles (within Wales) | 20 | 11.11%
| 4 | Outside Wales | 10 | 5.556%
| 5 | Total employees | 180 |  |  |  | 0.5 | 0.6 | 0.7 | 0.8 | 0.8 | This row used in star formula
| 6 | % within Wales |  | 94.44% | ***** |  | <50% | 50% - 60% | 60% - 70% | 70% - 80% | >80%
| K | Local suppliers and subcontractors | £ | Performance | Star rating | Comments
| 1 | Construction value | 2500000
| 2 | Total value of supplier and subcontract packages let to date | 1500000
| 3 | Welsh-let value to date | 1400000
| 4 | % of construction value let to date |  | 60% |  |  | 0.5 | 0.6 | 0.7 | 0.8 | 0.8 | This row used in star formula
| 5 | % within Wales |  | 93.33% | ***** |  | <50% | 50% - 60% | 60% - 70% | 70% - 80% | >80%
Note on D36: 10 = Defect free 9 = A few minor defects – no impact on end users 8 = Some defects with no significant impact on client or users; dealt with by maintenance 7 = Some defects – minor repairs needed; some impact on end users 6 = Some defects with some impact on end users; defects take some time to rectify and cause minor disruption to end users. 5 = Many defects with some impact on client or users; defects take some time to rectify and cause short-term disruption to users. 4 = Many defects with significant impact on users; planned rectification has a significant impact on end users. 3 = Major defects with major impact on client or users; require immediate and long term actions; rectification has large impact on end users. 2 = Several major and minor defects – many aspects unsatisfactory, only one or two just satisfactory; redesign and reconstruction needed to ensure satisfactory usage; considerable disruption to end users. 1 = Totally defective - defects so severe it is not be possible to use facility; long term rectification work required with large and long term impact on end users.

## End of Project perf (hidden)
End of Project KPI Report
#REF!
#REF! | #REF! | #REF! |  |  | Overall av of all scores
Company Performance overall |  | #REF! | Count responses (must equal 6 to trigger an overall star rating) |  | #REF! | No of stars | Overall av | PM av | CA av | CDMC av | Arch av | SV av | BSE av | CSE av | SCP av
Company performance | Quality of core services | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Timely delivery of services/information | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to key project objectives | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Collaborative approach | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Appropriate resourcing | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to safety | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
Client Performance overall |  | #REF! | Overall average | #REF! |  | No of stars | Av score | Individual scores |  |  | Av <6 | Av = 6-7 | Av = 7=8 | Av = 8-9 | Av = 9-10
Client performance | Quality of service delivery | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Timely delivery of information and decisions | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Clear aims and objectives | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Collaborative approach | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to project / appropriate resourcing of delivery team | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
| Commitment to safety | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
#REF!
Project performance overall |  | #REF! | Count responses (must equal 16 to trigger an overall star rating) | No. of stars | Weight | Score | Weighted average score for each cartegory | Count responses |  | Weightings in Col K are derived from KPI Plan
Cost | Project cost v Project allowance | ** | 1 | 2 | #REF! | #REF! | #REF! | 2 | ** | The stars are ratings from the END OF PROJECT PERF SHEET
| Project cost predictability | ***** | 1 | 5 | #REF! | #REF! |  |  | *****
Time | Project time predictability | **** | 1 | 4 | #REF! | #REF! | #REF! | 1 | ****
Quality | Quality of Design (AEDET) | ***** | 1 | 5 | #REF! | #REF! | #REF! | 3 | *****
| Defects - impact | **** | 1 | 4 | #REF! | #REF! |  |  | ****
| Defects - number at handover | * | 1 | 1 | #REF! | #REF! |  |  | *
Safety | Safety | **** | 1 | 4 | #REF! | #REF! | #REF! | 1 | ****
Sustainability | BREEAM | ***** | 1 | 5 | #REF! | #REF! | #REF! | 7 | *****
| Energy - CO2 - EPC | *** | 1 | 3 | #REF! | #REF! |  |  | ***
| Waste: Use of reused/recycled materials | ***** | 1 | 5 | #REF! | #REF! |  |  | *****
| Waste generation | *** | 1 | 3 | #REF! | #REF! |  |  | ***
| Waste to landfill | *** | 1 | 3 | #REF! | #REF! |  |  | 3 | *** | ***** | *** | *
| Use of local labour | ***** | 1 | 5 | #REF! | #REF! |  |  | *****
| Use of local suppliers/subcontractors | ***** | 1 | 5 | #REF! | #REF! |  |  | *****
|  |  | 14 |  | #REF! | #REF! | #REF! | 14 |  | 3 | 5 | 3 | 1
The row above averages waste to landfill scores into a single value
Waste to Landfill is calculated from the average for each category
The stars are converted to numbers in L42:O42
Then the rounded average is used in F38

## End of project summary (hidden)
End of Project Performance Summary
#REF!
#REF! | #REF! | #REF!
Key Performance Indicator | Weighted score | Rating
|  |  | Rounded scores | Overall star rating
Project performance - overall |  |  | #REF! | #REF!
Cost | #REF! | #REF! | #REF!
Time | #REF! | #REF! | #REF!
Quality | #REF! | #REF! | #REF!
Safety | #REF! | #REF! | #REF!
Sustainability | #REF! | #REF! | #REF!

## Summary SCP (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | SCP Performance
0 | Assessor |  |  | SCP | CA | PM | CDMC | SV | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Target |  | 7 | 7 | 7 | 7 | 7

## Summary CA (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | TCA Performance
0 | Assessor |  |  | SCP | CA | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | - | #REF! | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | - | #REF! | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | - | #REF! | #REF! | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | - | #REF! | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | - | #REF! | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | - | #REF! | #REF! | #REF!
|  |  | Target | 7 | 7 | 7 | 7

## Summary PM (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | PM Performance
0 | Assessor |  |  | SCP | CA | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | - | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | - | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timelines | #REF! | #REF! | - | #REF! | #REF! | Timelines | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | - | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | - | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | - | #REF! | #REF!
|  |  | Target | 7 | 7 | 7 | 7

## Summary HB (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | HB performance | [6 empty] | SCP | CA | PM | CDMC | SV | HB | Average
0 | Assessor |  |  | SCP | CA | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | #REF! | - | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | #REF! | - | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | #REF! | - | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | #REF! | - | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | #REF! | - | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | #REF! | - | #REF!
|  |  | Target | 7 | 7 | 7 | 7

## Summary SV (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | SV performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | #REF! | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | #REF! | #REF!
|  |  | Target | 7 | 7 | 7

## Summary CDMC (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | CDMC performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | #REF! | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | #REF! | #REF!
|  |  | Target | 7 | 7 | 7

## Summary Arch (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | Architect performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | #REF! | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | #REF! | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | #REF! | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | #REF! | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | #REF! | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | #REF! | #REF!
|  |  | Target | 7 | 7 | 7

## Summary CSE (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | CSE performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | - | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | - | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | - | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | - | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | - | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | - | #REF!
|  |  | Target | 7 | 7

## Summary BSE (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | BSE performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | - | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | - | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | - | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | - | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | - | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | - | #REF!
|  |  | Target | 7 | 7

## Summary BSI (hidden)
#REF! | #REF! |  |  | Performance Summary
#REF! | #REF! |  |  |  | BSI performance
0 | Assessor |  |  | SCP | PM | HB | Average |  |  | Target
#REF! | #REF! | A | Framework & role | #REF! | #REF! | - | #REF! | Framework & role | #REF! | 7
#REF! | #REF! | B | Service | #REF! | #REF! | - | #REF! | Service | #REF! | 7
#REF! | #REF! | C | Timeliness | #REF! | #REF! | - | #REF! | Timeliness | #REF! | 7
Date | #REF! | D | Collaboration | #REF! | #REF! | - | #REF! | Collaboration | #REF! | 7
|  | E | Safety | #REF! | #REF! | - | #REF! | Safety | #REF! | 7
|  | F | Overall performance | #REF! | #REF! | - | #REF!
|  |  | Target | 7 | 7

## Dashboard (hidden)
#REF! | #REF!
#REF! | Assessor | #REF!
| SCP Performance |  | SCP Performance
|  | #REF! |  | #REF!
| PM Performance |  | PM Performance
|  | #REF! |  | #REF!
| TCA Performance |  | TCA Performance
|  | #REF! |  | #REF!
| HB performance |  | HB performance
|  | #REF! |  | #REF!

## Dashboard (2) (hidden)
#REF! | #REF!
#REF! | Assessor | #REF!
| CDMC performance |  | CDMC performance
|  | #REF! |  | #REF!
| SV performance |  | SV performance
|  | #REF! |  | #REF!
| Architect performance |  | Architect performance
|  | #REF! |  | #REF!
| CSE performance |  | CSE performance
|  | #REF! |  | #REF!

## Dashboard (3) (hidden)
#REF! | #REF!
#REF! | Assessor | #REF!
| BSE performance |  | BSE performance
|  | #REF! |  | #REF!
| BSI performance |  | BSI performance
|  | #REF! |  | #REF!
| Architect performance |  | Architect performance
|  | #REF! |  | #REF!
| CSE performance |  | CSE performance
|  | #REF! |  | #REF!