## Sheet2 (hidden)
1.0 ACHIEVEMENTS FOLLOWING APPOINTMENT
This report sets out the progress as of 28/05/11 in delivering Cartrefi Cymunedol Gwynedd’s WHQS Refurbishment Programme. The tables below illustrates the key delivery tasks and progress made to date
1.1 Works Location |  |  |  | 1.3 Installations
LIP Area | Location Name |  | Percentage Complete | Building Elements | Completions to Date | Total Properties | Percentage to date
B1 | Maesgeirchen, Tan y Bryn |  | 30.93% | Door Replacement | 394 | 2852 | 13.81%
B2 | Coed Mawr, Penrhos, Treborth, Penchwintan, Tai Station, Maestryfan |  | 0% | Window Replacement | 239 | 1324 | 18.05%
B3 | Hirael, Central Bangor, Upper Bangor, Mynydd Llandegai, Glasinfryn, Tregarth, Tal y Bont, Bethesda |  | 0%
C1 | Maes Barcer, Maes Eilian, Bro Seiont,
C2 | Maesincla, Hendre, Caernarfon Town Centre, Bontnewydd
C3 | Y Felinheli, Bethel, Llanrug, Deiniolen, Rhiwlas, Llanberis, Cwm-y-Glo, Llanberis
C4 | Upper Llandwrog, Groeslon, Saron, Penygroes, Nantlle, Talsysarn, Llanllyfni, Nebo, Rhyd Ddu
D1 | Pwllheli Town West of Cob, Pwllheli Town East of Cob, Abersoch, Aberdaron, Mynytho, Penrhos, Llannor
D2 | Abererch, Criccieth, Porthmadog
D3 | Nefyn, Tudweiliog, Clynnog Fawr
M1 | Penrhyndeudraeth, Harlech, Llanbedr, Barmouth, Dyffryn Ardudwy
M2 | Dolgellau, Corris, Aberllefenni, Tywyn, Aberdyfi, Pennal
M3 | Llanffestiniog, Gellilydan, Trawsfynydd, Blaenau Ffestiniog, Bala, Llanuwchllyn Llanfor, Llandderfel
1.2 Contract Details
Activity | Position to Date
Contract Start Date | 2011-01-04
Contract Finish Date | 2012-09-30
| Doors | Windows
Total Properties | 2319 | 1324
Number of Properties Omitted | 44 | 0
Number of Properties Refused | 1 | 0
Number of Properties Open | 30 | 29
Number of Properties at Offer | 42 | 5
Number of Properties Completed to Date | 394 | 239
Ahead/On/Behind Target | Behind

## Heating (hidden)
Investment Programme Key Performance Indicators ALL PACKAGES
No. | Topic | Background | Measurement | Acceptable Performance | Unacceptable Performance - Reporting Trigger | Mode of collection | Frequency of collection | Frequency of reporting | Calculated
KP1 1 | Customer Satisfaction - Service | Satisfaction of the customer of service | Returned Customer Satisfaction Survey Form based on 75% return rate | 90% | <85% | Contractor - Collection of Customer Satisfaction Survey, Audited by Cartrefi Cymunedol Gwynedd | Rolling programme | Monthly | Average of Q? Customers overall rating on Contractor service
KPI 2 | Performance | Satisfaction of the client with performance of Constructor | Returned Satisfaction Questionnaire | 90% | <80% | CCG - CoW completes and returns satisfaction questionnaire | Daily site inspection | Monthly | Average of Q? CoW overall rating on Contractor performance
KP1 3 | Defects | Zero Major operational defects at contractor's completion offer | Senior Project Surveyor audits on completion | 0 | >5% properties rejected | CCG - CoW audits on completion | On inspection at contractors initial completion offer | Monthly | Rejected properties divided by completed properties X 100
KP1 4 | Programme | Completions per week and duration targets will be used together to ensure that the programme numbers are delivered during any one year. | Defined against contractor proposed programme of work subject to access | 100% | 95% (If not workload could br reduced) | Contractor - Contractor Monthly Return (Tracker) | Monthly | Per Project | Actual completions divided by programmed completions X 100
KP1 5 | Duration targets | To meet average duration targets as set out in the Strategic Brief | Number of Properties completed out of timescale - Completion date minus start date | 100% | <95% - Assessed on individual merit | Contractor - Contractor Monthly Return (Tracker) | Rolling Programme | Monthy | Number of Properties Completed within Target divided by Number of Properties Completed x 100
KP1 6 | Cost | Managing the budget both per contract and for the Client across the programme as a whole | The cost of variations against AMP (Year 1). March 2010 | 0% | 2% under AMP or 0% over at end of phase | Contractor - Contractor AMP Monitoring Form TBA | Monthly | Monthly | Forecasted AMP divided by agreed AMP X 100
KP1 7 | Defects (defects liability period) | Post completion - 12 months following completion of works | Defects relating to poor workmanship reported post handover | 5% (No reported warrented defects during DLP) | 15% (15% of properties with reported defects) | Contractor - Contractor Monthly Return | Rolling Programme | Monthly | No. of Defects Reported to-date divided by Units Complete X 100
KP1 8 | Response to Complaints | Complaints arising during and post completion. To be developed in accordance with current Cartrefi Cymunedol Gwynedd policy | Response to complaints within an agreed timescale | 0% outside timescale | >5% outside timescale | Contractor - Contractor Monthly Return | Monthly | Monthly | Total No. of Complaints outside timescale divided by No. of complaints X 100
KP1 9 | Health and safety | Data specific to Clients projects | To be reported in accordance with National Average | 0 | > than national average | Contractor - Contractor Monthly Return | Monthly | Monthly | Actual Vs National Average
KP1 10 | Training and Employment | Data specific to Clients projects | Number of Apprentices/Trainees generated through the project | In accordance with Contractors tender proposals.Numbers from ITT .Appendix 7 Pro Forma | < than Contractors tender proposals | Contractor - Contractor Monthly Return | Monthly | Monthly | Actual number of Apprentices/Trainees Vs numbers set out in Contractor proposals

## Sheet4 (hidden)
1.1 Works Location |  | 1.2 Contract Details |  |  | 1.3 Installations
LIP Area | Location Name | Activity | Position to Date |  | Building Elements | Completions to Date | Total Properties | Percentage to date
B1 | Maesgeirchen, Tan y Bryn | Contract Start Date | 2011-01-04 |  | Door Replacement | 849 | 2647 | 32.07%
B2 | Coed Mawr, Penrhos, Treborth, Penchwintan, Tai Station, Maestryfan | Contract Finish Date | 2012-09-30 |  | Window Replacement | 386 | 1197 | 32.25%
B3 | Hirael, Central Bangor, Upper Bangor, Mynydd Llandegai, Glasinfryn, Tregarth, Tal y Bont, Bethesda |  | Doors | Windows
C1 | Maes Barcer, Maes Eilian, Bro Seiont, | Total Properties | 2866 | 1343
C2 | Maesincla, Hendre, Caernarfon Town Centre, Bontnewydd | Number of Properties Omitted | 219 | 146
C3 | Y Felinheli, Bethel, Llanrug, Deiniolen, Rhiwlas, Llanberis, Cwm-y-Glo, Llanberis | Number of Properties Declined | 2 | 2
C4 | Upper Llandwrog, Groeslon, Saron, Penygroes, Nantlle, Talsysarn, Llanllyfni, Nebo, Rhyd Ddu | Number of Properties Open | 63 | 31
D1 | Pwllheli Town West of Cob, Pwllheli Town East of Cob, Abersoch, Aberdaron, Mynytho, Penrhos, Llannor | Number of Properties at Offer | 20 | 10
D2 | Abererch, Criccieth, Porthmadog | Number of Properties Completed to Date | 849 | 386
D3 | Nefyn, Tudweiliog, Clynnog Fawr
M1 | Penrhyndeudraeth, Harlech, Llanbedr, Barmouth, Dyffryn Ardudwy
M2 | Dolgellau, Corris, Aberllefenni, Tywyn, Aberdyfi, Pennal
M3 | Llanffestiniog, Gellilydan, Trawsfynydd, Blaenau Ffestiniog, Bala, Llanuwchllyn Llanfor, Llandderfel

## Signature
Key Performance Indicators
Asbestos Surveying Services - Lot 1 - Asbestos Framework
Dated
Scheme
The monthly Key Performance Indicators for Asbestos Surveying Services for Adra (Tai) Cyfyngedig.
Signed on behalf
The service provider
Signed on behalf
Adra (Tai) Cyfyngedig

## Scheme Totals
Asbestos Surveying
Scheme: | Asbestos management
Service Provider:
Total Assets | 6230
Number of P405 Asbestos Management trained Adra Staff | 3
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Darren Owen posib checkio’r ffigwr yma a just wirio’r ddogfen yma. Dwi wedi newid dyddiadau I cyd fynd hefo framework start date December Reply: Bore da @Sophie Williams, mae ffigwr yma dal yr un peth, mae o'n cadarnhau faint o hen stoc sydd ar ol(pre 2000)

## Summary
ASBESTOS MANAGEMENT
| KPI | Optimum Performance | Acceptable Performance | Unacceptable Performance | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | Cumulative
1 | Appointments attended within timescale | 100% | 90 - 95% | < 90% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
2 | Surveys achieving acceptable level of sampling | 100% | 90 - 95% | < 90% | #REF! | #REF! | #REF! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #REF! | #DIV/0!
3 | Non Conformances raised | 0 | 1 | >1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0
4 | Re-scheduled surveys | 0% | 2 - 5% | >5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0!

## KPI 1 - Appointments
KPI 1 - Requests per month
| 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | Cumulative
Surveys/Sampling/Air monitoring requested | [12 empty] | 0
Completed within allocated timescale | [12 empty] | 0
Not completed within allocated timescale | [12 empty] | 0
Percentage completed within timescale | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Timescales for surveying/sampling
This KPI is based on the following; Void properties = 5 working day turnaround means surveying the property and providing Adra with a completed survey within 5 working days of receiving our instruction and a keysafe being present on the property.
Tenanted properties = 10 working day turnaround means surveying the property and providing Adra with a completed survey within 10 working days of receiving our instruction. This is based on the tenant's contact details being correct, and the tenant willing to accept an appointment within the first 4 days of contact being made.
Timescale for air monitoring = Any scheduled air monitoring has to be carried out within 24 hours of the appointment being made (emergency air tests need to carried out within 4 hours of reported incident). We will expect to receive the results of any air tests within 24 hours of the site visit, and that air test certificates are provided on the day of the air test and left on site with a Adra member of staff or relevant contractor.

## KPI 2 - Sampling
KPI 2 - Results from Surveys/Sampling
| 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | Cumulative
Number of surveys with acceptable sampling | [12 empty] | 0
Number of surveys with unacceptable sampling | [12 empty] | 0
Total surveys carried out | [12 empty] | 0
Percentage achieving target | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
This KPI is based on surveys achieving a minimum of 4 samples on management surveys, and a minimum of 6 samples on R&D surveys with management throughout

## KPI 3 - Non Conformances
KPI 3 - Non Conformances raised
| 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | Cumulative
Non Conformances raised | [12 empty] | 0
Surveys requested | [12 empty] | 0
This KPI is based on surveys/airtests not being carried within the allocated timescales (see appointments tab)

## KPI 4 - Re-scheduled
KPI 4 - Re-scheduled surveys
| 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | Cumulative
No of properties re-scheduled | [12 empty] | 0
No of surveys raised | [12 empty] | 0
% Properties re-scheduled | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
This KPI is based on the number of re-visits booked in due to no access (nobody available to let surveyor in, or surveyor missed the scheduled appointment)

## KPI 11 (hidden)
KPI 11 - WASTE MANAGEMENT
Lovell | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled | Estimated per Month (Te) | Estimated per Month (Te)
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01
2011-04-01 | 2011-03-01
2011-05-01 | 2011-04-01 | 8.28 | 7.628 | 0.66 | 92.13%
2011-06-01 | 2011-05-01 | 19.6 | 18.068 | 1.532 | 92.18%
2011-07-01 | 2011-06-01 | 16.3 | 13.45 | 2.85 | 82.52%
2011-08-01 | 2011-07-01 | 33.52 | 26.77 | 6.75 | 79.86%
2011-09-01 | 2011-08-01 | 40.53 | 37.17 | 3.36 | 91.71%
2011-10-01 | 2011-09-01 | 58.986 | 52.036 | 6.98 | 88.22%
2011-11-01 | 2011-10-01 | 69.98 | 64.38 | 5.6 | 92%
2011-12-01 | 2011-11-01 | 71.47 | 64.98 | 6.49 | 90.92%
2012-01-01 | 2011-12-01 | 39.1 | 31.39 | 7.71 | 80.28%
2012-02-01 | 2012-01-01
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 357.766 | 315.872 | 41.932 | 88.29%
Nationwide | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01 | 14.4 | 13.97 |  | 97.01%
2011-04-01 | 2011-03-01 | 5.6 | 5.32 |  | 95%
2011-05-01 | 2011-04-01 | 7.8 | 7.72 |  | 98.97%
2011-06-01 | 2011-05-01 | 33.6 | 32.26 |  | 96.01%
2011-07-01 | 2011-06-01 | 29.1 | 28.23 |  | 97.01%
2011-08-01 | 2011-07-01 | 31.1 | 30.17 |  | 97.01%
2011-09-01 | 2011-08-01 | 19 | 18.43 |  | 97%
2011-10-01 | 2011-09-01 | 22.9 | 21.76 |  | 95.02%
2011-11-01 | 2011-10-01 | 27.8 | 26.97 |  | 97.01%
2011-12-01 | 2011-11-01 | 27.1 | 25.75 |  | 95.02%
2012-01-01 | 2011-12-01 | 22.6 | 22.19 |  | 98.19%
2012-02-01 | 2012-01-01
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 241 | 232.77 | 0 | 96.59%
EWE | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01 |  |  |  | #DIV/0!
2011-04-01 | 2011-03-01 |  |  |  | #DIV/0!
2011-05-01 | 2011-04-01 |  |  |  | #DIV/0!
2011-06-01 | 2011-05-01 |  |  |  | #DIV/0!
2011-07-01 | 2011-06-01 |  |  |  | #DIV/0!
2011-08-01 | 2011-07-01 |  |  |  | #DIV/0!
2011-09-01 | 2011-08-01 |  |  |  | #DIV/0!
2011-10-01 | 2011-09-01 |  |  |  | #DIV/0!
2011-11-01 | 2011-10-01 |  |  |  | #DIV/0!
2011-12-01 | 2011-11-01 | 0.25 | 0.25 | 0 | 100%
2012-01-01 | 2011-12-01 | 5 | 4.75 | 0.25 | 95%
2012-02-01 | 2012-01-01 | 6 | 5.25 | 0.75 | 87.5%
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 11.25 | 10.25 | 1 | 91.11%
Gelli | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01 |  |  |  | #DIV/0!
2011-04-01 | 2011-03-01 |  |  |  | #DIV/0!
2011-05-01 | 2011-04-01 |  |  |  | #DIV/0!
2011-06-01 | 2011-05-01 |  |  |  | #DIV/0!
2011-07-01 | 2011-06-01 |  |  |  | #DIV/0!
2011-08-01 | 2011-07-01 |  |  |  | #DIV/0!
2011-09-01 | 2011-08-01 |  |  |  | #DIV/0!
2011-10-01 | 2011-09-01 |  |  |  | #DIV/0!
2011-11-01 | 2011-10-01 |  |  |  | #DIV/0!
2011-12-01 | 2011-11-01
2012-01-01 | 2011-12-01 | 48 | 3 | 45 | 6.25%
2012-02-01 | 2012-01-01 | 76 | 1 | 75 | 1.316%
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 124 | 4 | 120 | 3.226%
PH Jones | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01 |  |  |  | #DIV/0!
2011-04-01 | 2011-03-01 |  |  |  | #DIV/0!
2011-05-01 | 2011-04-01 |  |  |  | #DIV/0!
2011-06-01 | 2011-05-01 |  |  |  | #DIV/0!
2011-07-01 | 2011-06-01 |  |  |  | #DIV/0!
2011-08-01 | 2011-07-01 |  |  |  | #DIV/0!
2011-09-01 | 2011-08-01 |  |  |  | #DIV/0!
2011-10-01 | 2011-09-01 |  |  |  | #DIV/0!
2011-11-01 | 2011-10-01 |  |  |  | #DIV/0!
2011-12-01 | 2011-11-01 |  |  |  | #DIV/0!
2012-01-01 | 2011-12-01 | 5.28 | 3.96 | 1.32 | 75%
2012-02-01 | 2012-01-01
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 5.28 | 3.96 | 1.32 | 75%
DLO | Month No. | Total Tonnage (Te) | Tonnage Recycled (Te) | Tonnage to Landfill (Te) | % Waste Recycled
2011-02-01 | 2011-01-01
2011-03-01 | 2011-02-01
2011-04-01 | 2011-03-01
2011-05-01 | 2011-04-01
2011-06-01 | 2011-05-01
2011-07-01 | 2011-06-01
2011-08-01 | 2011-07-01
2011-09-01 | 2011-08-01
2011-10-01 | 2011-09-01
2011-11-01 | 2011-10-01
2011-12-01 | 2011-11-01
2012-01-01 | 2011-12-01
2012-02-01 | 2012-01-01
2012-03-01 | 2012-02-01
2012-04-01 | 2012-03-01
|  | 0 | 0 | 0 | 0%

## Summary - Monthly (hidden)
KPI |  | Acceptable Performance | Gelli | EWE | Lovell External | Nationwide D | Nationwide W
1 | Customer (Tenant) Satisfaction | 90% | #REF! | #REF! |  | #REF!
2 | Performance | 90% | #REF! | #REF! | #REF! | #REF!
3 | Defects | 0% | #REF! | #REF! | n/a | #REF! | #REF!
4 | Programme | 100% | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Duration Targets | 100% | #REF! | #REF! | n/a | #REF! | #REF!
6 | Cost | 100%
7 | Defects (defects liability period) | 5%
8 | Response to Comments | 5% | #REF! | #REF! | n/a | #REF!
9 | Health and Safety | 100% | #REF! | #REF! | #REF! | #REF!
10 | Training and Employment | 15% | #REF! | #REF! | #REF! | #REF!
11 | Waste Management | 85% | 1.316% | 87.5% | 80.28%
KPI |  | Acceptable Performance | Lovell Internal | Lovell Heating | Loft Insulation | GM Jones | Apollo | Falconer | DLO | PH Jones
1 | Customer (Tenant) Satisfaction | 90% | #REF! | #REF! | n/a | #REF! | #REF! | n/a | #REF! | n/a
2 | Performance | 90% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Defects | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Programme | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Duration Targets | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Defects (defects liability period) | 5%
8 | Response to Comments | 5% | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | 0%
9 | Health and Safety | 100% | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
10 | Training and Employment | 15% | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
11 | Waste Management | 85% | 80.28% | [6 empty] | 0%

## Summary - Cumulative (hidden)
KPI |  | Acceptable Performance | Gelli | EWE | Lovell External | Nationwide D | Nationwide W
1 | Customer (Tenant) Satisfaction | 90% | #REF! | #REF! | n/a | #REF!
2 | Performance | 90% | #REF! | #REF! | #REF! | #REF!
3 | Defects | 0% | #REF! | #REF! | n/a | #REF! | #REF!
4 | Programme | 100% | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Duration Targets | 100% | #REF! | #REF! | n/a | #REF! | #REF!
7 | Defects (defects liability period) | 5%
8 | Response to Comments | 5% | #REF! | #REF! | n/a | #REF!
9 | Health and Safety | 100% | #REF! | #REF! | #REF! | #REF!
10 | Training and Employment | 15% | #REF! | #REF! | #REF! | #REF!
11 | Waste Management | 85% | 3.226% | 91.11% | 88.29% | 96.59%
KPI |  | Acceptable Performance | Lovell Internal | Lovell Heating | Loft Insulation | GM Jones | Apollo | Falconer | DLO | PH Jones
1 | Customer (Tenant) Satisfaction | 90% | #REF! | #REF! | n/a | #REF! | #REF! | n/a | #REF! | n/a
2 | Performance | 90% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Defects | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Programme | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Duration Targets | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | Defects (defects liability period) | 5%
8 | Response to Comments | 5% | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | 0%
9 | Health and Safety | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | Training and Employment | 15% | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
11 | Waste Management | 85% | 88.29% | [6 empty] | 75%