## Instructions
William Aston Hall RIBA Feasibility Study - Pricing Schedule
Instructions to Tenderers
1 | Complete all yellow cells. Do not overwrite formulas in total rows.
2 | Prices should be submitted in GBP and exclusive of VAT unless stated otherwise. VAT will be calculated separately.
3 | The fixed price for the core commission should include all staff time, management, coordination, ordinary expenses, meetings, reporting, QA and production of final outputs.
4 | The University is seeking a proportionate RIBA Stage 1 feasibility study. Optional or stretch items should be priced separately and will only be instructed if affordable and approved.
5 | Tenderers should identify any assumptions, exclusions, information requirements or risks in the Assumptions sheet.
6 | Tenderers should state whether any costs are dependent on the availability of drawings, surveys, operating data, stakeholder availability or site access.
7 | The approved project budget is £50,000 including VAT. Tenderers should therefore be clear about the level of work that can be delivered within their fixed fee.
Project | William Aston Hall RIBA Feasibility Study
Client | Wrexham University
Funding | Arts Council of Wales Arts Capital Investment Fund
Budget | £50,000 including VAT total project budget, comprising £40,000 ACW funding and £10,000 University match
Project closure | Final invoices, grant claim evidence and closure requirements by 4 March 2027
VAT rate to apply | 20%
Currency | GBP
Submitted by
Date submitted

## Core Pricing
Core Fee Schedule - RIBA Stage 1 Feasibility Study
Ref | Core activity / deliverable | Expected coverage | Lead discipline(s) | Fixed fee excl. VAT | VAT | Total incl. VAT | Tenderer notes / assumptions
C1 | Project inception and brief confirmation | Inception meeting, information request, confirmation of methodology, programme, responsibilities and stakeholder plan. | Lead consultant / PM |  | 0 | 0
C2 | Information review and baseline assessment | Review available drawings, previous reports, access information, operating information, grant requirements and known constraints. | Lead consultant / architect / theatre consultant |  | 0 | 0
C3 | Site review and existing venue appraisal | Walkthrough of front of house, auditorium, stage, backstage, access routes, loading, plant/interface areas and adjacent spaces. | Architect / theatre consultant / technical specialists |  | 0 | 0
C4 | Stakeholder engagement and workshops | Proportionate engagement with Wrexham University, Theatr Clwyd, operational users and other agreed stakeholders. | Lead consultant / theatre consultant |  | 0 | 0
C5 | Audience journey, front of house and venue functionality | Review arrival, foyer, toilets, bar/hospitality, circulation, dwell, wayfinding, crowd flow and civic/University use. | Architect / theatre consultant / access consultant |  | 0 | 0
C6 | Auditorium, seating, acoustics and technical theatre review | Build on existing seating/acoustic work. Consider seating flexibility, sightlines, sound/control positions, acoustic needs, PA implications and technical infrastructure. | Theatre consultant / acoustician / technical theatre |  | 0 | 0
C7 | Stage, backstage, loading and performer facilities | Review stage access, backstage accommodation, dressing rooms, green room, loading, storage, wing space, technical limitations and performer experience. | Theatre consultant / architect / technical theatre |  | 0 | 0
C8 | Access and inclusion improvement schedule | Access baseline and prioritised improvement schedule covering audiences, artists, staff and University users. Include immediate, operational and future capital items. | Access consultant / architect / theatre consultant |  | 0 | 0
C9 | Heritage and listed building constraints | Proportionate review of listed status and heritage constraints/opportunities, identifying issues for next stage and likely consent implications. | Conservation architect / architect |  | 0 | 0
C10 | Building services, sustainability and environmental comfort | High-level review of comfort, ventilation, heating/cooling, controls, lighting, energy implications, running costs and sustainability opportunities. | MEP / sustainability consultant |  | 0 | 0
C11 | Operating model and commercial implications | High-level consideration of operating implications, revenue opportunities, bar/hospitality, hires, ticketing, University use and future procurement implications. | Theatre consultant / commercial adviser |  | 0 | 0
C12 | Options appraisal | Develop proportionate longlist/shortlist options and compare benefits, complexity, cost, operational impact, access, sustainability and deliverability. | Lead consultant with full team |  | 0 | 0
C13 | Cost ranges, phasing and delivery risks | Broad order cost ranges, phasing advice, survey/design information gaps, procurement considerations and risk commentary. | QS / lead consultant |  | 0 | 0
C14 | Draft report and Project Board presentation | Draft feasibility report and presentation to Project Board for review and direction. | Lead consultant |  | 0 | 0
C15 | Final report and editable outputs | Final integrated feasibility report, executive summary, options matrix, cost/phasing note, risk/assumptions register and recommended next-stage route. | Lead consultant with full team |  | 0 | 0
Total Core Fixed Fee |  |  |  | 0 | 0 | 0
Budget comparison - Core fee excl. VAT against approved £50,000 project budget |  |  |  | -50000 | Within budget

## Optional Items
Optional / Separately Priced Items
Part A: Optional items
Ref | Optional item | Description / trigger | Basis of price | Fixed fee excl. VAT | VAT | Total incl. VAT | Tenderer notes / exclusions
O1 | Measured survey / CAD drawing verification | Only if existing drawings are insufficient for feasibility work. | Fixed fee / allowance |  | 0 | 0
O2 | Detailed access audit | More detailed audit beyond baseline/access improvement schedule, including user testing if required. | Fixed fee |  | 0 | 0
O3 | Additional disabled user / lived experience engagement | Targeted engagement beyond core stakeholder allowance. | Per session / fixed fee |  | 0 | 0
O4 | Acoustic modelling | Modelling of shortlisted acoustic interventions and PA implications. | Fixed fee |  | 0 | 0
O5 | Detailed MEP survey or energy modelling | Detailed survey/modelling beyond high-level feasibility review. | Fixed fee |  | 0 | 0
O6 | Heritage impact assessment / conservation statement | If required to support later consent or funding stage. | Fixed fee |  | 0 | 0
O7 | Planning/listed building pre-application support | Support with early discussions with planning/conservation officers. | Fixed fee / day rate |  | 0 | 0
O8 | Detailed business plan / operating model financial model | More detailed financial modelling beyond high-level operating implications. | Fixed fee |  | 0 | 0
O9 | Funding bid support | Support with drafting or appendices for future capital funding applications. | Day rate / fixed fee |  | 0 | 0
O10 | Additional stakeholder workshop | Additional workshop above the number included in the core fee. | Per workshop |  | 0 | 0
O11 | 3D visualisations / presentation graphics | Additional visuals beyond proportionate sketches/diagrams in the core report. | Per image / fixed fee |  | 0 | 0
Total Optional Items (Part A) |  |  |  | 0 | 0 | 0
Please amend the activities and deliverables required for Stage 2. Where an activity does not apply to Stage 2, enter £0 and state "Not applicable" in column H. Use line S2.C16 for any additional Stage 2 work.
Part B: Stage 2 Concept Design fee breakdown
Ref | Activity / deliverable | Expected coverage | Lead discipline(s) | Fixed fee excl. VAT | VAT | Total incl. VAT | Tenderer notes / assumptions
S2.C1 | Project inception and brief confirmation | Inception meeting, information request, confirmation of methodology, programme, responsibilities and stakeholder plan. | Lead consultant / PM |  | 0 | 0
S2.C2 | Information review and baseline assessment | Review available drawings, previous reports, access information, operating information, grant requirements and known constraints. | Lead consultant / architect / theatre consultant |  | 0 | 0
S2.C3 | Site review and existing venue appraisal | Walkthrough of front of house, auditorium, stage, backstage, access routes, loading, plant/interface areas and adjacent spaces. | Architect / theatre consultant / technical specialists |  | 0 | 0
S2.C4 | Stakeholder engagement and workshops | Proportionate engagement with Wrexham University, Theatr Clwyd, operational users and other agreed stakeholders. | Lead consultant / theatre consultant |  | 0 | 0
S2.C5 | Audience journey, front of house and venue functionality | Review arrival, foyer, toilets, bar/hospitality, circulation, dwell, wayfinding, crowd flow and civic/University use. | Architect / theatre consultant / access consultant |  | 0 | 0
S2.C6 | Auditorium, seating, acoustics and technical theatre review | Build on existing seating/acoustic work. Consider seating flexibility, sightlines, sound/control positions, acoustic needs, PA implications and technical infrastructure. | Theatre consultant / acoustician / technical theatre |  | 0 | 0
S2.C7 | Stage, backstage, loading and performer facilities | Review stage access, backstage accommodation, dressing rooms, green room, loading, storage, wing space, technical limitations and performer experience. | Theatre consultant / architect / technical theatre |  | 0 | 0
S2.C8 | Access and inclusion improvement schedule | Access baseline and prioritised improvement schedule covering audiences, artists, staff and University users. Include immediate, operational and future capital items. | Access consultant / architect / theatre consultant |  | 0 | 0
S2.C9 | Heritage and listed building constraints | Proportionate review of listed status and heritage constraints/opportunities, identifying issues for next stage and likely consent implications. | Conservation architect / architect |  | 0 | 0
S2.C10 | Building services, sustainability and environmental comfort | High-level review of comfort, ventilation, heating/cooling, controls, lighting, energy implications, running costs and sustainability opportunities. | MEP / sustainability consultant |  | 0 | 0
S2.C11 | Operating model and commercial implications | High-level consideration of operating implications, revenue opportunities, bar/hospitality, hires, ticketing, University use and future procurement implications. | Theatre consultant / commercial adviser |  | 0 | 0
S2.C12 | Options appraisal | Develop proportionate longlist/shortlist options and compare benefits, complexity, cost, operational impact, access, sustainability and deliverability. | Lead consultant with full team |  | 0 | 0
S2.C13 | Cost ranges, phasing and delivery risks | Broad order cost ranges, phasing advice, survey/design information gaps, procurement considerations and risk commentary. | QS / lead consultant |  | 0 | 0
S2.C14 | Draft report and Project Board presentation | Draft feasibility report and presentation to Project Board for review and direction. | Lead consultant |  | 0 | 0
S2.C15 | Final report and editable outputs | Final integrated feasibility report, executive summary, options matrix, cost/phasing note, risk/assumptions register and recommended next-stage route. | Lead consultant with full team |  | 0 | 0
S2.C16 | Other Stage 2 activities (please specify) | Any Stage 2 Concept Design work not covered by the activities above. Describe the work in column H. | As required |  | 0 | 0
Total Stage 2 Fee (Part B) |  |  |  | 0 | 0 | 0
Total Optional Items (Parts A and B) |  |  |  | 0 | 0 | 0

## Day Rates
Team, Day Rates and Core Allocation
Ref | Role / discipline | Organisation | Named individual | Role in commission | Day rate excl. VAT | Core days included | Core fee equivalent | Notes
D1 | Lead consultant / project lead |  |  | Overall coordination, client contact, Project Board reporting and integrated final report |  |  | 0
D2 | Architect / lead designer |  |  | Existing building review, spatial options, briefing and design coordination |  |  | 0
D3 | Theatre / venue consultant |  |  | Venue operation, programming implications, audience journey, theatre functionality and commercial opportunities |  |  | 0
D4 | Technical theatre consultant |  |  | Stage, sound, lighting, flying/rigging, technical infrastructure, operational flexibility |  |  | 0
D5 | Acoustician |  |  | Review existing acoustic work, advise on further interventions and future modelling requirements |  |  | 0
D6 | Access / inclusive design adviser |  |  | Access baseline, inclusive design priorities and access improvement schedule |  |  | 0
D7 | Building services / sustainability consultant |  |  | Environmental comfort, services constraints, energy, lighting, ventilation and sustainability opportunities |  |  | 0
D8 | Quantity surveyor / cost consultant |  |  | Broad order cost ranges, phasing, assumptions and cost risk commentary |  |  | 0
D9 | Fire consultant |  |  | High-level fire strategy constraints, capacity/access implications and next-stage requirements |  |  | 0
D10 | Heritage / conservation adviser |  |  | Listed building constraints, significance and next-stage consent considerations |  |  | 0
D11 | Administrative / report support |  |  | Meeting notes, document control, formatting and issue of outputs |  |  | 0
Total day-rate equivalent of core allocation | [6 empty] | 0

## Payment Profile
Proposed Payment Profile
Milestone | Indicative timing | Output / trigger | % of core fee | Amount excl. VAT | VAT | Total incl. VAT | Tenderer comments
P1 | On appointment / inception | Inception meeting completed and inception note issued | 20% | 0 | 0 | 0
P2 | Baseline / engagement complete | Baseline assessment and stakeholder engagement summary issued | 20% | 0 | 0 | 0
P3 | Emerging options | Options longlist/shortlist, initial costs and risks issued | 25% | 0 | 0 | 0
P4 | Draft report | Draft feasibility report and Project Board presentation issued | 25% | 0 | 0 | 0
P5 | Final report / closure | Final report, editable outputs, final invoice and claim evidence issued | 10% | 0 | 0 | 0
Total payment profile |  |  | 100% | 0 | 0 | 0

## Assumptions
Tenderer Assumptions, Exclusions and Information Requirements
Ref | Category | Assumption / exclusion / risk | Impact on price or programme | Information required from University / Theatr Clwyd | Date required
A1 | Drawings / surveys
A2 | Asbestos / intrusive access
A3 | Stakeholder availability
A4 | Theatr Clwyd operating data
A5 | Existing technical information
A6 | Access information / audit baseline
A7 | Planning / heritage information
A8 | Expenses / travel
A9 | Meetings / workshops included
A10 | Items excluded from fixed fee